## Integration Map
HealthConnect Week 6 — Workstream Integration Map
Shows how workstreams connect and what information/output flows between them.
Integration ID | From Workstream | To Workstream | Input / Output | Why Relevant | PM Coordination Role | Evidence Required | Status
INT-001 | Data Analytics | Data Science | Validated analytical findings | Can inform modelling decisions | Track dependency and resulting decision | Validated analysis/report | Pending Evidence
INT-002 | Data Science | ML Engineering | Candidate model and interface requirements | Enables pipeline integration | Monitor readiness and dependency | Model artefact/interface documentation | Pending Evidence
INT-003 | ML Engineering | Data Science | Pipeline/model validation feedback | Can reveal compatibility issues | Track issue and resolution | Integration test result | Pending Evidence
INT-004 | GenAI | Project Management | Assistant evaluation findings, issues and dependencies | Supports readiness and risk decisions | Capture issues, risks and decisions | Evaluation output | Pending Evidence
INT-005 | Project Management | All Workstreams | Priorities, risks, issues, decisions and timelines | Provides project governance | Coordinate integrated controls | Updated PM workbook | PM Control
INT-006 | All Workstreams | All Workstreams | Relevant outputs for integrated solution | Supports common HealthConnect objective | Monitor readiness and unresolved dependencies | Updated deliverables/validation evidence | Pending Evidence

## Integration Register
HealthConnect Week 6 — Integration & Dependency Register
Tracks dependencies affecting integration readiness and Week 7 sequencing.
ID | From Track | To Track | Dependency / Required Output | Type | Potential Impact | Priority | Owner | Status | Required Action | Evidence
DINT-001 | Data Analytics | Data Science | Validated findings relevant to attendance/no-show decisions | Analytical | Model decisions may lack validated business context | High | Data Analytics / PM | Completed - PM Integration | Use validated Week 5 analytics findings to update PM integration priorities and Week 7 testing preparation | HealthConnect_Week5_Analysis.pdf
DINT-002 | Data Science | ML Engineering | Validated candidate model and interface requirements | Technical | Pipeline integration may be delayed | High | Data Science / ML Engineering | Pending Evidence | Confirm model interface and requirements | To be attached/linked
DINT-003 | ML Engineering | Data Science | Pipeline/model compatibility validation | Technical | Integration defects may affect testing | High | ML Engineering / Data Science | Pending Evidence | Record validation outcome and unresolved issues | To be attached/linked
DINT-004 | GenAI | Project Management | Assistant evaluation/refinement findings | Information / Safety | Readiness and risk assessment may be incomplete | Medium | GenAI / PM | Pending Evidence | Review evidence and update risks/issues | To be attached/linked
DINT-005 | Project Management | All Tracks | Integration priorities, timeline, risks, issues and decisions | Project Governance | Uncoordinated work can create bottlenecks | High | PM | Active | Maintain integrated controls and escalate blockers | Week 6 PM workbook
DINT-006 | Data Analytics | Project Management | Week 5 analytical findings on no-show patterns and remaining analysis | Analytical / Planning | PM may miss evidence-based priorities and testing considerations | High | Data Analytics / PM | Active - Informed | Carry findings into integration controls, dependency tracking and Week 7 testing/refinement preparation | HealthConnect_Week5_Analysis.pdf

## Integration Readiness
HealthConnect Week 6 — Integration Readiness Assessment
Readiness is evidence-based; do not mark technical outputs ready without supporting evidence.
Workstream | Expected Output | Evidence Available? | Readiness | Reason / Gap | Dependency | Action Before Week 7 | PM Owner
Data Analytics | Advanced Analytics & Decision Support | Yes - Week 5 analysis received | Integrated / PM Evidence Available | Week 5 analysis provides validated findings and identifies remaining analytical work; downstream technical use is not claimed | Analytics findings inform PM priorities and Week 7 preparation | Use findings in testing/refinement coordination; verify any downstream modelling use separately | PM
Data Science | Model Improvement & Validation | Not verified | Pending Evidence | Improved model/validation not verified | Candidate model/interface | Verify model and validation evidence | PM
ML Engineering | Integrated ML Pipeline | Not verified | Pending Evidence | Pipeline evidence not verified | Validated model/interface | Verify integration testing evidence | PM
Generative AI | AI Assistant Evaluation & Refinement | Not verified | Pending Evidence | Evaluation/refinement evidence not verified | Evaluation findings | Verify evidence and update controls | PM
Project Management | Integration & Coordination Package | Yes — PM artefacts | In Progress | Integration controls are being established | Technical evidence needed for full readiness | Maintain evidence-based status | PM

## Integration Issue Log
HealthConnect Week 6 — Integration Issue Log
Records actual integration issues and the actions needed to resolve them.
Issue ID | Week | Issue Description | Affected Tracks | Impact | Priority | Owner | Status | Action / Resolution | Escalation | Evidence / Notes
ISS-001 | Week 6 | Verified technical workstream outputs are not currently available in the PM record | PM / Technical Tracks | Full integration readiness cannot be confirmed | High | PM | Open | Obtain/review verified outputs and update readiness | Yes, near testing gate | Current evidence limitation
ISS-002 | Week 6 | Formal Week 4 Excel timeline was not previously finalised | PM | Potential inconsistency across PM artefacts | Medium | PM | Open | Maintain one central relative-week timeline | No | Continuation from Week 5
ISS-003 | Week 6 | Initial cross-track integration was blocked because no verified technical output was available at the time of the first coordination attempt; subsequently, a Data Analytics Week 5 output was received and reviewed with PM. | PM / Data Science / Data Analytics | Mandatory Week 6 integration evidence was initially incomplete; Data Analytics → PM integration is now evidenced. | High | PM | Resolved - Analytics Integration Completed | Document the completed Data Analytics → PM exchange and resulting PM use; retain other technical-output gaps as separate issues. | Yes, before/at Week 7 testing gate | HealthConnect_Week5_Analysis.pdf + collaboration record

## Decision Log
HealthConnect Week 6 — Project Decision Log
Records material PM decisions, rationale and follow-up.
Decision ID | Week | Decision | Rationale | Project Impact | Owner | Status | Follow-up
DEC-001 | Week 6 | Use evidence-based integration readiness statuses | Do not claim technical readiness without supporting output | Improves reporting accuracy | PM | Active | Update when evidence is verified
DEC-002 | Week 6 | Prioritise dependencies that could affect Week 7 testing | Testing depends on sufficiently integrated components | Focuses PM attention on critical blockers | PM | Active | Review before testing gate
DEC-003 | Week 6 | Continue from Week 5 rather than rebuild identical PM deliverables | Week 6 requires progression and meaningful improvement | Preserves continuity | PM | Active | Use Week 5 controls as baseline
DEC-004 | Week 6 | Use relative project weeks in timeline | No verified calendar dates in PM evidence | Avoids unsupported dates | PM | Active | Add actual dates only when verified
DEC-005 | Do not claim cross-track integration as completed without an actual exchanged output and resulting change | No verified technical workstream output was received despite an attempt to obtain one | Protects reporting accuracy and keeps Week 6 evidence defensible | Cross-track integration remains an open requirement for Week 7 follow-up
DEC-006 | Week 6 | Use the Data Analytics Week 5 findings as a PM integration input and carry identified remaining analytical work into Week 7 preparation | The received analysis provides evidence on no-show patterns and explicitly identifies remaining multi-variable analysis and appointment-time-slot KPI work | Improves evidence-based prioritisation, dependency tracking and testing/refinement preparation without claiming downstream technical use | PM | Active | Verify any later Data Science/ML use separately; monitor remaining analytics items before testing

## Updated Timeline
HealthConnect Week 6 — Updated Project Timeline
Relative project weeks are used to avoid unsupported calendar dates.
WBS / Activity | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | PM Status | Notes
1.0 Problem Understanding | ● |  |  |  |  | Completed | Week 4 foundation
1.1 Project Initiation & Planning | ● |  |  |  |  | Completed | Charter, scope, stakeholders, WBS
1.2 Resource & Data Review | ● | ● |  |  |  | Completed / Continuing | Approved resources remain in use
1.3 Initial Risk & Dependency Identification | ● | ● |  |  |  | Updated | Expanded into integration controls
2.0 Analysis and Solution Design |  | ● | ● |  |  | In Progress | PM monitors dependencies
2.1 Appointment Attendance Analysis |  | ● | ● |  |  | Pending technical evidence | Analytics output required for verified integration
2.2 No-Show Prediction Problem Definition |  | ● | ● |  |  | Pending technical evidence | Relevant to Data Science
2.3 AI Assistant Solution Design |  | ● | ● |  |  | Pending technical evidence | Relevant to GenAI
2.4 ML System Design |  | ● | ● |  |  | Pending technical evidence | Relevant to ML integration
2.5 Integrated Solution Planning |  |  | ● | ● |  | In Progress | PM coordinates integration/testing readiness
3.0 Development |  |  | ● | ● | ● | Planned / Continuing | Technical development progresses
4.0 Testing and Refinement |  |  |  | ● | ● | Planned | Week 7 testing/refinement
5.0 Final Presentation | [5 empty] | Planned for Week 8 | Final integration/presentation

## Updated Risk Register
HealthConnect Week 6 — Updated Risk Register
Focus: integration, readiness, dependencies and risks affecting Week 7 testing.
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Level | Mitigation / Response | Owner | Status | Week 6 Change
R001 | Appointment data may contain missing/incomplete records affecting analysis/model development | Data | Medium | High | High | Apply data-quality checks and document missing fields | Data Analytics / Data Science | Open | Continues
R002 | Project scope may expand beyond HealthConnect objectives | Scope | Medium | High | High | Maintain scope boundaries and change control | PM | Open | Continues
R003 | Delays across tracks may affect dependent activities and integration | Schedule / Integration | Medium | High | High | Monitor dependencies and escalate blockers | PM | Open | Reassessed for integration
R004 | Conflicting priorities or limited availability may delay work | Resource | Medium | Medium | Medium | Clarify responsibilities, priorities and escalation | PM | Open | Continues
R005 | Dependencies between workstreams may create integration bottlenecks | Dependency / Integration | Medium | High | High | Maintain integration register and readiness criteria | PM | Open | Greater focus in Week 6
R006 | AI assistant may provide information outside approved Knowledge Base | AI / Safety | Low | High | High | Restrict scope and apply escalation/validation controls | GenAI / PM | Open | Continues
R007 | Requirements may not be clearly understood across workstreams | Requirements | Medium | Medium | Medium | Document requirements, assumptions and decisions | PM | Open | Continues
R008 | Communication gaps may cause inconsistent integration understanding | Communication | Medium | Medium | Medium | Use coordination records and decision tracking | PM | Open | Continues
R009 | Technical limitations may affect development or integration | Technical | Medium | Medium | Medium | Identify dependencies and alternatives | Technical Tracks | Open | Continues
R010 | Outputs may not be completed within internship timeframe | Schedule | Medium | High | High | Prioritise critical deliverables and monitor readiness | PM | Open | Continues
R011 | Technical workstream evidence may not be available when PM needs to assess readiness | Integration / Evidence | Medium | High | High | Verify outputs by track; Data Analytics evidence is now available, while other technical outputs remain subject to verification. | PM | Open | Partially reduced by receipt of Data Analytics evidence; remains active for other technical workstreams | Confirmed as active constraint in Week 6
R012 | Integration issues may remain unresolved before Week 7 testing | Integration / Testing | Medium | High | High | Use issue log, owners, priorities and readiness gate; carry remaining technical integration gaps into Week 7. | PM | Open | Data Analytics → PM integration completed; other integration pathways remain unverified | Remains active because integration evidence is incomplete

## Read Me
HealthConnect Week 6 — PM Workbook Guide
Central PM control workbook for integration, dependencies, issues, decisions, timeline and risks.
Item | Guidance
Step 1 | Integration Map — workstream relationships and information/output flows.
Step 2 | Integration Register — dependencies affecting integration readiness.
Step 3 | Integration Readiness — evidence-based readiness assessment.
Step 4 | Integration Issue Log — actual integration issues requiring action.
Step 5 | Decision Log — material PM decisions and rationale.
Step 6 | Updated Timeline — progression using relative project weeks.
Step 7 | Updated Risk Register — Week 4/5 risks plus Week 6 integration risks.
Evidence rule | Never mark another track's technical output completed/integrated without evidence.
Cross-track rule | Communication alone is not integration; integration requires a meaningful change, improvement, decision or validated output.

## Unresolved Issues
Unresolved Issues
Issues requiring attention before the project can be considered ready for Week 7 testing.
Issue ID | Issue | Affected Area | Impact | Priority | Owner | Status | Required Action | Testing Gate Relevance
UI-001 | Verified technical workstream outputs are not yet available in the PM evidence set | Integration / PM | Limits confirmation of full integration readiness | High | PM / Relevant Track Owners | Open | Obtain or review verified outputs and update readiness assessment | High
UI-002 | Additional cross-track integration may be required for other technical pathways, but one meaningful Data Analytics → PM activity is now evidenced. | Cross-Track Integration | Other technical integration pathways remain unverified; the mandatory integration requirement has a documented Data Analytics → PM evidence point. | High | PM / Relevant Track | Open | Continue verification of GenAI/Data Science/ML Engineering outputs; do not treat planned pathways as completed without evidence. | High
UI-003 | Formal Week 4 Excel timeline was not previously finalised | Timeline / PM | Potential inconsistency across project artefacts | Medium | PM | Open | Use the Week 6 relative-week timeline as the central schedule baseline | Medium
UI-004 | Technical readiness cannot be inferred from the PM plan alone | Readiness | Risk of overstating project progress | High | PM | Open | Keep technical items as Pending Evidence until supporting artefacts are verified | High
UI-005 | Other technical workstream integration evidence remains to be verified after the completed Data Analytics → PM exchange. | Data Science / ML Engineering / GenAI integration | Full multi-workstream integration readiness cannot yet be confirmed. | High | PM / Relevant Track Owners | Open | Obtain and verify remaining technical outputs and document any resulting integration changes. | High

## Cross-Track Coordination
Cross-Track Coordination
Record actual Week 6 integration activity. Current entries distinguish planned/pending coordination from verified completion.
Record ID | Track Collaborated With | Project Dependency | Information / Output Received | Information / Output Provided | Integration Activity | What Changed | Evidence | Status
CTR-001 | Data Analytics | Validated analytical findings informing PM/project decisions | Week 5 Data Analytics analysis: booking lead time and previous no-show history showed strongest relationships with no-shows; appointment type had comparatively limited influence; remaining analysis was identified. | PM integration requirements, dependency/risk context, and Week 7 testing/refinement considerations. | Reviewed the received Data Analytics output against the HealthConnect objective and incorporated its findings/remaining work into PM integration and testing coordination. | PM now has an evidence-based analytical input for prioritisation and Week 7 preparation; remaining analytics work is tracked. No downstream model use is claimed. | HealthConnect_Week5_Analysis.pdf + collaboration messages | Completed
CTR-002 | Data Science | Candidate model/readiness information relevant to project sequencing | Pending verification | PM dependency, timeline and testing-readiness requirements | Planned integration point identified; actual exchange not yet verified | No change claimed until evidence is available | Evidence to be attached/linked | Pending Evidence
CTR-003 | ML Engineering | Pipeline integration/readiness information | Pending verification | PM integration controls and Week 7 testing coordination requirements | Planned integration point identified; actual exchange not yet verified | No change claimed until evidence is available | Evidence to be attached/linked | Pending Evidence
CTR-004 | Generative AI | Assistant evaluation/refinement findings affecting safety/readiness | Pending verification | PM risk, issue and readiness controls | Planned integration point identified; actual exchange not yet verified | No change claimed until evidence is available | Evidence to be attached/linked | Pending Evidence
CTR-005 | Data Science / Data Analytics | Actual cross-track output required to validate Week 6 integration | No verified technical output received | Requested a relevant Week 6 workstream update/output for integration review | Attempted to obtain and review a technical-track output; no integration change could be validated | No technical change claimed because no output was received | Documented as an integration attempt/blocker rather than completed collaboration | Week 6 coordination attempt; no technical artifact received | Blocked