HealthConnect Clinic Experience Lab

Week 6 Project Summary

Project Management Track | AnalystLab Africa Experience Lab Internship

Project: Improving Patient Appointment Attendance and Healthcare Support Using Data and AI

Central Question: How can HealthConnect Clinic use data and AI to reduce missed appointments and improve the patient support experience?

# Week 6 Summary

1. Planned: Integrate the HealthConnect workstreams, update dependencies and risks, validate integration readiness, document issues and decisions, and prepare coordination for Week 7 testing/refinement.

2. Completed: The PM integration controls were updated, and a meaningful Data Analytics → Project Management integration was completed using the Week 5 Data Analytics analysis output.

3. Improved from Week 5: The work moved from task-level execution control to evidence-based integration control, including integration readiness, dependency tracking, issue/decision logging, and explicit Week 7 testing preparation.

4. Integrated: The Data Analytics Week 5 analysis was received and reviewed as an input to PM integration. The findings, limitations, and remaining analytical work were incorporated into PM coordination records.

5. Collaborated Track(s): Data Analytics. Other technical pathways remain pending evidence in the PM record.

6. Information Exchanged: Data Analytics provided its Week 5 appointment attendance/no-show analysis, including key findings, relevant factors/features, limitations, and remaining analysis. PM provided the integration context, dependencies, priorities, and Week 7 testing/refinement focus.

7. What Changed: The analytical findings are now represented as a documented PM integration input. Booking lead time and previous no-show history are treated as important analytical considerations; remaining analytical work and limitations are carried into Week 7 planning. No unverified downstream model use is claimed.

8. Findings / Outcomes: The received analysis identified booking lead time and previous no-show history as important factors associated with no-shows, while appointment type showed limited influence. The analysis also identified remaining multi-variable analysis and a fourth KPI as Week 6/next-stage work.

9. Challenges: Verified technical outputs from Data Science, ML Engineering, and GenAI were not available in the PM record. This limit claims about full technical integration and requires continued evidence-based readiness tracking.

10. Decisions: Maintain evidence-based readiness; do not claim integration without actual exchange/change; prioritize dependencies affecting Week 7; use the Data Analytics output as PM integration evidence; carry remaining analytical work forward without claiming downstream technical use.

11. Remaining Issues: Other technical integration evidence remains pending; some analytical work remains; unresolved project risks/dependencies require monitoring; the earlier Week 4 timeline finalization issue remains documented.

12. PM Contribution: Maintained the integration map, dependency and risk controls, issue and decision logs, evidence-based readiness status, cross-track coordination record, and Week 7 testing/refinement coordination.

13. Week 7 Focus: Coordinate testing and refinement readiness, verify remaining technical outputs, track unresolved dependencies/issues, validate end-to-end alignment against requirements, and document evidence for the next testing stage.

# Evidence Basis

The completed cross-track integration is supported by the Data Analytics Week 5 analysis output received and reviewed by the Project Management track. The PM record documents how the output was used for integration coordination and Week 7 testing preparation. No downstream use by Data Science, ML Engineering, or GenAI is claimed without verified evidence.

# Week 6 Overall Status

In Progress — Data Analytics → PM Integration Completed / Other Technical Readiness Pending Evidence

# Week 7 Priority

Move into testing and refinement coordination, verify remaining technical outputs, resolve or escalate integration dependencies, and maintain evidence-based validation against the HealthConnect requirements.