## Stakeholder Register
Stakeholder ID | Stakeholder | Role | Interest | Influence | Expectations | Communication Method | Communication Frequency | Engagement Strategy | Owner
ST-01 | Client Executive Sponsor | Approves funding and major decisions | High | High | Successful project delivery and business value | Executive meetings, Email | Bi-weekly | Manage Closely | Project Manager
ST-02 | Project Manager | Plans and manages the project | High | High | Project delivered on time and within scope | Meetings, Project reports | Weekly | Manage Closely | Self
ST-03 | Business Analyst | Gathers business requirements | High | Medium | Clear and approved requirements | Workshops, Meetings | Weekly | Keep Engaged | Project Manager
ST-04 | AI Engineers | Develop the AI solution | High | High | Clear technical requirements | Daily stand-up, Teams | Daily | Manage Closely | Technical Lead
ST-05 | Data Analysts | Prepare and analyze customer data | High | Medium | Access to quality data | Meetings, Email | Weekly | Keep Engaged | Project Manager
ST-06 | Software Developers | Integrate the AI solution | High | Medium | Stable requirements and timely decisions | Stand-up meetings | Daily | Keep Engaged | Technical Lead
ST-07 | IT Support Team | Supports infrastructure and deployment | Medium | Medium | Clear deployment plan | Email, Meetings | Weekly | Keep Informed | Project Manager
ST-08 | Marketing Team | Uses customer insights for campaigns | High | Medium | Actionable customer insights | Demonstrations, Email | Monthly | Keep Informed | Project Manager
ST-09 | End Users | Use the AI solution | High | Low | Easy-to-use and reliable system | Training sessions | Monthly | Keep Informed | Project Manager
ST-10 | Quality Assurance (QA) Tester | Tests the solution before deployment | High | Medium | Stable requirements, adequate testing time, and prompt issue resolution | Meeting, Test Reports, Email | Weekly(Daily during Testing) | Keep Engaged | Project Manager
ST-11 | Cloud Engineer | Management cloud infrastructure and deployment | High | High | Clear infrastructure requirements, timely approvals, and secure deployment | Technical Meetings, Microsoft Teams, Email | Weekly | Manage Closely | Technical Lead
ST-12 | Change Management Lead | Supports user adoption and organisational change | High | Medium | Effective communication, user readiness, and successful adoption of the new system | Workshops, Email, Training Sessions | Bi-Weekly | Keep Engaged | Project Manager