## Risk Register
Risk ID | Risk Description | Category | Probability | Impact | Risk Level | Mitigation Strategy | Risk Owner | Status
R-01 | Poor customer data quality may affect AI model performance. | Data | High | High | High | Perform data profiling, validation, and cleansing before model development. | Data Analyst | Open
R-02 | Project activities may be delayed due to resource constraints. | Schedule | Medium | High | High | Develop a realistic schedule, monitor progress weekly, and reallocate resources when necessary. | Project Manager | Open
R-03 | Stakeholders may resist adopting the new AI solution. | Change Management | Medium | Medium | Medium | Engage stakeholders early, provide regular updates, and conduct user training. | Project Manager | Open
R-04 | Data security or privacy breaches could occur. | Security | Low | High | Medium | Implement access controls, encrypt sensitive data, and comply with data protection policies. | IT Support Lead | Open
R-05 | Integration with existing systems may be more complex than expected. | Technical | Medium | High | High | Conduct early technical assessments and integration testing. | Technical Lead | Open
R-06 | Project costs may exceed the available budget. | Financial | Medium | Medium | Medium | Monitor project expenses regularly and obtain approval for major changes. | Project Manager | Open
R-07 | Key project team members may become unavailable. | Resource | Low | High | Medium | Cross-train team members and maintain proper project documentation. | Project Manager | Open
R-08 | Changes to project requirements may lead to scope creep. | Scope | Medium | High | High | Use a formal change control process and obtain approval for scope changes. | Project Manager | Open
R-09 | Delay in AI model training. | Schedule | Medium | High | High | Break development into smaller tasks, monitor progress weekly, and allocate additional technical resources if require. | AI Engineer Lead | Open
R-10 | Cloud service outage. | Infrastructure | Low | High | Medium | Select a reliable cloud provider, monitor service availability, and perform regular backups. | Cloud Engineer | Open
R-11 | Key team member becomes unavailable during execution. | Resource | Medium | Medium | Medium | Cross-train team members and maintain up-to-date project documentation. | Project Manager | Open
R-12 | Vendor delivery delay. | Procurement | Low | Medium | Low | Confirm delivery dates early and monitor vendor performance. | Project Manager | Open
R-13 | AI model produces inaccurate or biased predictions due to poor-quality training data. | AI/Data Quality | Medium | High | High | Validate and clean training data, test the model thoroughly, and review outputs with business experts. | Data Analyst | Open
R-14 | Design defects are identified late, leading to rework and project delays. | Quality | Medium | High | High | Conduct a formal quality review before approving the solution design. | QA Tester | Open

## Risk Matrix
Probability \ Impact | Low | Medium | High
High | Medium | High | High
Medium | Low | Medium | High
Low | Low | Low | Medium