## Communication Plan
Communication Plan
Stakeholder | Information to Communicate | Method | Frequency | Sender
Client Executive Sponsor | Project progress, key decisions, major risks | Progress meeting and email | Bi-weekly | Project Manager
Project Team | Task assignments, project updates, issues | Team meetings | Weekly | Project Manager
Executive Sponsor | Executive status report | Meeting | Monthly | Project Manager
AI Engineers | Technical requirements and development updates | Daily stand-up | Daily | Technical Lead
Data Analysts | Data preparation activities and issues | Team meeting | Weekly | Project Manager
IT Support Team | Infrastructure and deployment updates | Email and meeting | Weekly | Project Manager
Technical Team | Sprint review/Technical review | Team meeting | Weekly | Project Manager
End Users | Training schedule, system updates, user guides | Training sessions and email | Before deployment and after go-live | Project Manager
Communication Principles
Information should be clear, accurate, and timely.
Communication methods should match stakeholder needs.
Major project risks and issues should be reported immediately.
Progress should be reviewed regularly to support informed decision-making.
All key project decisions should be documented for future reference.