HEALTHCONNECT CLINIC

WEEK 5 PROGRESS / STATUS REPORT

Project Execution & Progress Management

| Field | Details |
| --- | --- |
| Project | HealthConnect Clinic Experience Lab |
| Project Title | Improving Patient Appointment Attendance and Healthcare Support Using Data and AI |
| Professional Track | Project Management |
| Reporting Period | Week 5 |
| Report Status | Version 1.0 |
| Execution Context | Individual online internship assignment |

# 1. Executive Status

Week 5 focused on moving the HealthConnect project from the Week 4 planning foundation into an execution and progress-management structure. The Project Management work completed in this reporting package converts the Week 4 WBS into actionable tasks, establishes responsible workstreams and priorities, defines evidence-based status categories, updates the project timeline, and establishes controls for risks, dependencies, issues, decisions and track coordination.

Because this internship is being completed individually online and no direct cross-track status updates were available, this report does not claim technical-track completion, meetings, communications, assignments or results that were not evidenced. Technical activities are therefore recorded as planned or awaiting workstream update.

# 2. Week 5 Objectives

Review the Week 4 project plan and translate major activities into actionable tasks.

Establish priorities and responsible workstreams for execution monitoring.

Create a practical mechanism for tracking project progress.

Update the high-level project timeline.

Review existing risks and dependencies and identify execution-stage risks.

Establish a coordination approach for the Project Management and technical workstreams.

Document project issues, decisions, constraints and Week 6 transition priorities.

# 3. Status Summary

| Area | Week 5 Status | Status Basis |
| --- | --- | --- |
| Week 4 PM foundation review | Completed | Week 4 charter, scope, stakeholder, WBS, risk/dependency and communication framework reviewed. |
| Actionable task structure | Completed | Major WBS activities converted into trackable execution tasks. |
| Responsible workstream mapping | Planned / established | Tasks mapped to PM, Data Analytics, Data Science, ML Engineering and Generative AI. |
| Task priority framework | Planned / established | High/Medium/Low priority structure defined. |
| Progress tracking | Planned / established | Evidence-based status categories defined in the PM control workbook. |
| Updated timeline | Planned / established | Relative Week 4–12 timeline formalised in the Excel control package. |
| Risk review | Planned / established | Week 4 risks retained and Week 5 execution risks added. |
| Dependency review | Planned / established | Existing dependencies retained and status-evidence dependency added. |
| Track coordination | Planned / established | Coordination points, information flows and escalation approach documented. |
| Technical-track progress | Awaiting Workstream Update | No direct technical-track progress evidence was available to the individual PM intern. |

# 4. Execution Management Approach

The Week 5 approach uses a single Project Management control workbook to maintain consistency across the task tracker, updated project plan, timeline, risk register, dependency register, issues log, decision log and track coordination plan. This reduces the risk of conflicting versions across separate files.

## 4.1 Status Definitions

| Status | Meaning |
| --- | --- |
| Completed | The PM activity has been completed and there is supporting project documentation/evidence. |
| Planned | The activity is identified as required but has not been evidenced as completed. |
| Awaiting Workstream Update | The activity belongs to a technical workstream for which no direct progress evidence is available. |
| At Risk | Used only when a documented condition creates a credible threat to delivery. |
| Blocked | Used only when a confirmed blocker prevents progress. |

# 5. Key Execution Controls

| Control | Purpose | Week 5 Application |
| --- | --- | --- |
| Task Tracker | Monitor actionable work | Tasks broken down by ID, workstream, priority, dependency, status and evidence basis. |
| Timeline | Monitor schedule | Relative project weeks maintained from Week 4 through Week 12. |
| Risk Register | Monitor threats | Week 4 risks reviewed and four execution/governance risks added. |
| Dependency Register | Monitor prerequisites | Data, knowledge, scope, coordination, development and reporting dependencies tracked. |
| Issues Log | Capture problems/gaps | Known execution and artifact-control issues documented without inventing events. |
| Decision Log | Record PM decisions | Key governance choices documented with rationale. |
| Track Coordination | Manage handoffs | Planned information flows and coordination points established across workstreams. |

# 6. Key Risks and Dependencies

Several Week 4 risks remain relevant during execution, particularly scope expansion, schedule delays, workstream dependencies, data quality, communication gaps and the internship timeframe. Week 5 also introduces governance risks around unavailable workstream status evidence, artifact version consistency, unclear ownership and the risk of treating assumptions as confirmed facts.

The HealthConnect appointment dataset and Data Dictionary remain important dependencies for Data Analytics and Data Science. The Clinic Knowledge Base remains an important dependency for Generative AI work. The Knowledge Base defines an approved assistant scope centred on administrative and informational support and requires escalation for unavailable or out-of-scope requests.

# 7. Major Issues Encountered

| Issue | Impact | Response |
| --- | --- | --- |
| No direct cross-track status updates in the individual online setting | Technical progress cannot be verified through direct collaboration evidence. | Use evidence-based status labels and document coordination as planned mechanisms rather than completed interactions. |
| Formal Week 4 Excel timeline was not previously finalised as a file | Schedule control required a formal workbook representation. | Formalised the timeline in the Week 5 PM control workbook. |
| Potential inconsistency across separate PM artifacts | Could create conflicting versions of project information. | Use one PM control workbook as the master execution-control package. |

# 8. Decisions Made

Use “Responsible Workstream” rather than “Assigned To” to avoid implying that another intern was directly assigned work.

Use evidence-based status categories to prevent unsupported technical-track completion claims.

Use one PM control workbook as the central execution-control package.

Use relative project weeks rather than invented calendar dates because an official project calendar was not provided.

# 9. Cross-Track Coordination

No direct cross-track collaboration is claimed for Week 5. Instead, a coordination framework was established for the expected relationships between Project Management and the technical workstreams. This includes monitoring milestones, capturing inputs and outputs, identifying dependencies, recording blockers, and escalating issues where appropriate.

| Coordination Point | Relevant Handoff | Purpose |
| --- | --- | --- |
| PM ↔ Data Analytics | Dataset/Data Dictionary → analysis findings/KPIs → PM tracking | Support evidence-based project monitoring and decisions. |
| PM ↔ Data Science | Data readiness → modelling status/results → PM tracking | Monitor predictive-work dependencies and readiness. |
| PM ↔ ML Engineering | Requirements → implementation status/issues → PM tracking | Monitor technical implementation dependencies and blockers. |
| PM ↔ Generative AI | Clinic Knowledge Base → prototype/testing evidence → PM tracking | Monitor approved scope, safety testing and escalation requirements. |
| Cross-workstream integration | Milestone outputs → dependent-workstream readiness | Identify handoff risks and support integrated delivery. |

# 10. Changes from the Week 4 Approach

Moved from high-level planning to actionable task-level control.

Introduced explicit workstream responsibility mapping.

Introduced evidence-based progress status categories.

Added execution-stage risks concerning status visibility, ownership, artifact control and assumptions.

Added an issues log and decision log to strengthen project governance.

Formalised cross-track coordination as a planned mechanism rather than representing unverified collaboration as completed activity.

# 11. Week 6 Focus

Continue monitoring the project against the updated timeline.

Review available workstream evidence and update task statuses when verified information becomes available.

Monitor critical risks and dependencies and escalate confirmed issues.

Track analysis and solution-design milestones.

Review whether technical outputs remain aligned with the agreed project scope and central problem.

Prepare for the transition from analysis/solution design into development activities.

# 12. Overall Assessment

The Week 5 Project Management work establishes a practical execution-control layer on top of the Week 4 project foundation. The main achievement is not a claim of technical completion; it is the creation of a structured mechanism for turning planned work into trackable activities, monitoring dependencies and risks, recording decisions and issues, and coordinating the expected workstream handoffs.

The project remains in an execution and solution-development stage. Technical progress should be updated only when supporting evidence becomes available.