## Project Dashboard
HEALTHCONNECT CLINIC — WEEK 5 PROJECT EXECUTION & PROGRESS PACKAGE
Project | HealthConnect Clinic Experience Lab
Project Title | Improving Patient Appointment Attendance and Healthcare Support Using Data and AI
Track | Project Management
Week | Week 5 — Project Execution & Progress Management
Execution Context | Individual online internship; technical-track progress is not claimed without evidence
Status Basis | Completed / Planned / Awaiting Workstream Update
Control Metrics |  | Control Note
Total Tasks | 48 | Technical-track completion is not fabricated. Unknown technical progress is recorded as Awaiting Workstream Update.
Completed | 2
Planned | 11
Awaiting Workstream Update | 35
High Priority | 40
Open Risks | 14
Open Dependencies | 9
Open Issues | 3

## Task Tracker
Task ID | Workstream | Task | Objective | Priority | Dependency | Responsible Workstream | Status | Evidence / Status Basis
PM-01 | Project Management | Review Week 4 project foundation | Confirm charter, scope, stakeholders, WBS, risks, dependencies and communication approach | High | Week 4 outputs | PM | Completed | Week 4 foundation reviewed
PM-02 | Project Management | Convert WBS activities into actionable tasks | Break major activities into trackable execution tasks | High | PM-01 | PM | Completed | Week 5 task structure
PM-03 | Project Management | Establish responsible workstreams | Map tasks to appropriate HealthConnect workstreams | High | PM-02 | PM | Planned | Responsible Workstream mapping
PM-04 | Project Management | Establish task priorities | Classify execution tasks by project importance | High | PM-02 | PM | Planned | Priority framework
PM-05 | Project Management | Establish project progress tracking | Define status categories and evidence expectations | High | PM-02 | PM | Planned | Task tracker
PM-06 | Project Management | Update project timeline | Reflect Week 5 execution and downstream milestones | High | PM-02 | PM | Planned | Updated timeline
PM-07 | Project Management | Review Week 4 risks | Determine which prior risks remain relevant | High | Week 4 Risk Register | PM | Planned | Updated risk register
PM-08 | Project Management | Review Week 4 dependencies | Review existing project dependencies and impacts | High | Week 4 Dependency Register | PM | Planned | Updated dependency register
PM-09 | Project Management | Identify new Week 5 risks | Capture execution-stage risks | Medium | PM-07 | PM | Planned | New risk entries
PM-10 | Project Management | Establish track coordination mechanism | Define inputs, outputs, checkpoints and escalation | High | PM-03 | PM | Planned | Track coordination plan
PM-11 | Project Management | Prepare Week 5 project status report | Document evidence-based status and constraints | High | PM-05 | PM | Planned | Status report
PM-12 | Project Management | Document major issues | Record known execution issues without inventing events | Medium | PM-05 | PM | Planned | Issues log
PM-13 | Project Management | Prepare Week 6 transition priorities | Identify remaining work and next-stage priorities | High | PM-11 | PM | Planned | Week 6 priorities
DA-01 | Data Analytics | Inspect appointment dataset | Inspect appointment dataset | High | Dataset + Data Dictionary | Data Analytics | Awaiting Workstream Update | No direct workstream update available
DA-02 | Data Analytics | Check data types and missing values | Check data types and missing values | High | DA-01 | Data Analytics | Awaiting Workstream Update | No direct workstream update available
DA-03 | Data Analytics | Check duplicates/inconsistent values | Check duplicates/inconsistent values | High | DA-01 | Data Analytics | Awaiting Workstream Update | No direct workstream update available
DA-04 | Data Analytics | Perform exploratory analysis | Perform exploratory analysis | High | DA-02; DA-03 | Data Analytics | Awaiting Workstream Update | No direct workstream update available
DA-05 | Data Analytics | Calculate selected KPIs | Calculate selected KPIs | High | DA-04 | Data Analytics | Awaiting Workstream Update | No direct workstream update available
DA-06 | Data Analytics | Create initial dashboard/visualisations | Create initial dashboard/visualisations | High | DA-04; DA-05 | Data Analytics | Awaiting Workstream Update | No direct workstream update available
DA-07 | Data Analytics | Develop business insights | Develop business insights | High | DA-05; DA-06 | Data Analytics | Awaiting Workstream Update | No direct workstream update available
DA-08 | Data Analytics | Document limitations/recommendations | Document limitations/recommendations | Medium | DA-07 | Data Analytics | Awaiting Workstream Update | No direct workstream update available
DS-01 | Data Science | Review ML problem definition | Review ML problem definition | High | Week 4 definition | Data Science | Awaiting Workstream Update | No direct workstream update available
DS-02 | Data Science | Prepare modelling dataset | Prepare modelling dataset | High | Dataset + Data Dictionary | Data Science | Awaiting Workstream Update | No direct workstream update available
DS-03 | Data Science | Assess missing/inconsistent records | Assess missing/inconsistent records | High | DS-02 | Data Science | Awaiting Workstream Update | No direct workstream update available
DS-04 | Data Science | Assess potential data leakage | Assess potential data leakage | High | DS-02 | Data Science | Awaiting Workstream Update | No direct workstream update available
DS-05 | Data Science | Engineer predictive features | Engineer predictive features | High | DS-03 | Data Science | Awaiting Workstream Update | No direct workstream update available
DS-06 | Data Science | Define train/test strategy | Define train/test strategy | High | DS-05 | Data Science | Awaiting Workstream Update | No direct workstream update available
DS-07 | Data Science | Train baseline classification model | Train baseline classification model | High | DS-06 | Data Science | Awaiting Workstream Update | No direct workstream update available
DS-08 | Data Science | Evaluate baseline model | Evaluate baseline model | High | DS-07 | Data Science | Awaiting Workstream Update | No direct workstream update available
DS-09 | Data Science | Document modelling limitations | Document modelling limitations | Medium | DS-08 | Data Science | Awaiting Workstream Update | No direct workstream update available
ML-01 | ML Engineering | Review Week 4 architecture | Review Week 4 architecture | High | Week 4 architecture | ML Engineering | Awaiting Workstream Update | No direct workstream update available
ML-02 | ML Engineering | Establish repository structure | Establish repository structure | High | ML-01 | ML Engineering | Awaiting Workstream Update | No direct workstream update available
ML-03 | ML Engineering | Implement data-processing workflow | Implement data-processing workflow | High | ML-02 | ML Engineering | Awaiting Workstream Update | No direct workstream update available
ML-04 | ML Engineering | Create reusable preprocessing components | Create reusable preprocessing components | Medium | ML-03 | ML Engineering | Awaiting Workstream Update | No direct workstream update available
ML-05 | ML Engineering | Implement initial model workflow | Implement initial model workflow | High | ML-03 | ML Engineering | Awaiting Workstream Update | No direct workstream update available
ML-06 | ML Engineering | Establish dependencies/configuration | Establish dependencies/configuration | Medium | ML-02 | ML Engineering | Awaiting Workstream Update | No direct workstream update available
ML-07 | ML Engineering | Document pipeline | Document pipeline | Medium | ML-03 | ML Engineering | Awaiting Workstream Update | No direct workstream update available
ML-08 | ML Engineering | Test pipeline components | Test pipeline components | High | ML-03; ML-05 | ML Engineering | Awaiting Workstream Update | No direct workstream update available
AI-01 | Generative AI | Review Week 4 assistant design | Review Week 4 assistant design | High | Week 4 design | Generative AI | Awaiting Workstream Update | No direct workstream update available
AI-02 | Generative AI | Develop approved-use-case prompts | Develop approved-use-case prompts | High | AI-01 + Knowledge Base | Generative AI | Awaiting Workstream Update | No direct workstream update available
AI-03 | Generative AI | Test prompt variations | Test prompt variations | High | AI-02 | Generative AI | Awaiting Workstream Update | No direct workstream update available
AI-04 | Generative AI | Integrate approved Knowledge Base information | Integrate approved Knowledge Base information | High | AI-02 | Generative AI | Awaiting Workstream Update | No direct workstream update available
AI-05 | Generative AI | Test supported questions | Test supported questions | High | AI-04 | Generative AI | Awaiting Workstream Update | No direct workstream update available
AI-06 | Generative AI | Test ambiguous questions | Test ambiguous questions | High | AI-04 | Generative AI | Awaiting Workstream Update | No direct workstream update available
AI-07 | Generative AI | Test unsupported requests | Test unsupported requests | High | AI-04 | Generative AI | Awaiting Workstream Update | No direct workstream update available
AI-08 | Generative AI | Test escalation scenarios | Test escalation scenarios | High | AI-04 | Generative AI | Awaiting Workstream Update | No direct workstream update available
AI-09 | Generative AI | Develop initial prototype/workflow | Develop initial prototype/workflow | High | AI-05; AI-06; AI-07; AI-08 | Generative AI | Awaiting Workstream Update | No direct workstream update available
AI-10 | Generative AI | Document limitations and next steps | Document limitations and next steps | Medium | AI-09 | Generative AI | Awaiting Workstream Update | No direct workstream update available

## Updated Project Plan
WBS ID | Stage | Major Activity | Responsible Workstream | Start | Finish | Priority | Status
1.0 | Problem Understanding | Maintain project foundation | PM | Week 4 | Week 5 | High | Completed
2.0 | Analysis & Solution Design | Coordinate analysis and solution-design prerequisites | PM + Technical Workstreams | Week 5 | Week 6 | High | Planned
3.0 | Development | Monitor development workstreams | PM + Technical Workstreams | Week 7 | Week 9 | High | Planned
4.0 | Testing & Refinement | Monitor integrated testing and issue resolution | PM + Technical Workstreams | Week 10 | Week 11 | High | Planned
5.0 | Final Presentation | Coordinate findings, documentation and presentation | PM + Technical Workstreams | Week 12 | Week 12 | High | Planned

## Timeline
WBS ID | Activity | Start | Finish | Status
1.0 | Problem Understanding | Week 4 | Week 4 | Completed
1.1 | Project Initiation & Planning | Week 4 | Week 4 | Completed
1.2 | Resource & Data Review | Week 4 | Week 5 | Planned
1.3 | Initial Risk & Dependency Identification | Week 4 | Week 5 | Planned
2.0 | Analysis and Solution Design | Week 5 | Week 6 | Planned
2.1 | Appointment Attendance Analysis | Week 5 | Week 6 | Planned
2.2 | No-Show Prediction Problem Definition | Week 5 | Week 6 | Planned
2.3 | AI Assistant Solution Design | Week 5 | Week 6 | Planned
2.4 | ML System Design | Week 5 | Week 6 | Planned
2.5 | Integrated Solution Planning | Week 6 | Week 6 | Planned
3.0 | Development | Week 7 | Week 9 | Planned
3.1 | Data Preparation | Week 7 | Week 8 | Planned
3.2 | Analytics Development | Week 8 | Week 9 | Planned
3.3 | Model Development | Week 8 | Week 9 | Planned
3.4 | AI Assistant Prototype | Week 8 | Week 9 | Planned
3.5 | Project Monitoring & Coordination | Week 7 | Week 9 | Planned
4.0 | Testing and Refinement | Week 10 | Week 11 | Planned
4.1 | Solution Testing | Week 10 | Week 10 | Planned
4.2 | AI Safety & Scope Testing | Week 10 | Week 10 | Planned
4.3 | Issue Resolution & Refinement | Week 10 | Week 11 | Planned
4.4 | Project Review | Week 11 | Week 11 | Planned
5.0 | Final Presentation | Week 12 | Week 12 | Planned
5.1 | Final Findings & Recommendations | Week 12 | Week 12 | Planned
5.2 | Final Documentation | Week 12 | Week 12 | Planned
5.3 | Final Presentation | Week 12 | Week 12 | Planned

## Risk Register
Risk ID | Category | Risk Description | Origin | Likelihood | Impact | Rating | Mitigation / Response | Owner | Status
R001 | Data | Appointment data may contain missing/incomplete records affecting analysis/modeling | Week 4 | Medium | High | High | Review data quality and document missing fields | Data Analytics / Data Science | Open
R002 | Scope | Scope may expand beyond agreed objectives | Week 4 | Medium | High | High | Maintain scope boundaries and change control | PM | Open
R003 | Schedule | Dependent workstream delays may affect downstream activities | Week 4 | Medium | High | High | Monitor milestones and dependencies | PM | Open
R004 | Resource | Limited availability or conflicting priorities may affect execution | Week 4 | Medium | Medium | Medium | Use clear responsibilities and prioritisation | PM | Open
R005 | Dependency | Dependencies between workstreams may create bottlenecks | Week 4 | Medium | High | High | Maintain dependency register and prerequisites | PM | Open
R006 | AI/Safety | AI assistant may provide information outside approved knowledge base | Week 4 | Low | High | High | Restrict to approved information and escalation rules | Generative AI | Open
R007 | Requirements | Requirements may not be clearly understood | Week 4 | Medium | Medium | Medium | Document and review requirements | PM | Open
R008 | Communication | Communication gaps may cause inconsistent understanding | Week 4 | Medium | Medium | Medium | Use documented decisions and escalation | PM | Open
R009 | Technical | Technical limitations may affect development or integration | Week 4 | Medium | Medium | Medium | Identify prerequisites and alternatives | Technical Workstreams | Open
R010 | Schedule | Outputs may not complete within internship timeframe | Week 4 | Medium | High | High | Prioritise critical deliverables | PM | Open
R011 | Execution | No direct cross-track status updates are available in the individual online setting | Week 5 | Medium | Medium | Medium | Use evidence-based status labels; avoid unsupported claims | PM | Open
R012 | Governance | Multiple artifact versions may create inconsistency | Week 5 | Medium | Medium | Medium | Use version naming and controlled master files | PM | Open
R013 | Ownership | Responsible workstream may be unclear | Week 5 | Medium | High | High | Maintain responsible-workstream mapping | PM | Open
R014 | Assumptions | Planning assumptions may be mistaken for confirmed facts | Week 5 | Medium | High | High | Clearly label assumptions and verified evidence | PM | Open

## Dependency Register
Dependency ID | Dependency | Dependent Activity | Type | Responsible Workstream | Criticality | Expected Condition | Status
D001 | HealthConnect appointment dataset | Data analysis/model preparation | Information | Data Analytics / Data Science | High | Dataset available and usable | Open
D002 | HealthConnect Data Dictionary | Correct interpretation of variables | Information | Data Analytics / Data Science | High | Dictionary available | Open
D003 | HealthConnect Clinic Knowledge Base | AI assistant design and safety boundaries | Information | Generative AI | High | Approved knowledge source available | Open
D004 | Scope and requirements | All workstreams | Project | All Workstreams | High | Week 4 scope foundation | Open
D005 | Analysis / solution design | Development | Technical / Process | Technical Workstreams | High | Design outputs completed | Open
D006 | Track coordination | Integrated solution | Team / Governance | PM + Technical Workstreams | High | Coordination mechanism established | Open
D007 | Required tools/resources | Development and documentation | Technical | Relevant Workstream | Medium | Required tools available | Open
D008 | Development completion | Testing and refinement | Process | Technical Workstreams | High | Initial implementation available | Open
D009 | Workstream status evidence | Accurate project reporting | Governance | PM | Medium | Verified status evidence available | Open

## Issues Log
Issue ID | Category | Issue | Owner | Impact | Action / Response | Status | Identified
ISS-001 | Execution governance | No direct cross-track status updates are available in the individual online internship setting | PM | Medium | Use evidence-based status labels; do not fabricate collaboration or completion | Open | Week 5
ISS-002 | Schedule control | Formal Week 4 Excel timeline was not previously finalised as a file | PM | Low | Create and maintain the formal Week 5 timeline workbook | Open | Week 5
ISS-003 | Artifact control | Multiple supporting files could become inconsistent if updated independently | PM | Medium | Use this workbook as the PM control package and version outputs | Open | Week 5

## Decision Log
Decision ID | Decision | Reason | Timing | Decision Owner | Status
DEC-001 | Use responsible workstream rather than assigned individual | Avoid implying direct assignment where no cross-track interaction occurred | Week 5 | PM | Approved
DEC-002 | Use evidence-based status categories | Prevent unsupported technical-track completion claims | Week 5 | PM | Approved
DEC-003 | Use one PM control workbook | Improve consistency across execution controls | Week 5 | PM | Approved
DEC-004 | Use relative project weeks | Official calendar dates were not provided | Week 5 | PM | Approved

## Track Coordination
Coordination ID | Coordination Point | Purpose | Expected Information Flow | Evidence Status | Responsible | Priority
CO-01 | PM ↔ Data Analytics | Monitor analysis milestones and capture data-quality findings, KPIs and insights | Dataset/Data Dictionary → findings → PM tracking | Planned mechanism; no direct interaction claimed | PM + Data Analytics | High
CO-02 | PM ↔ Data Science | Monitor modelling milestones and data dependencies | Data readiness → model status/results → PM tracking | Planned mechanism; no direct interaction claimed | PM + Data Science | High
CO-03 | PM ↔ ML Engineering | Monitor implementation prerequisites and blockers | Requirements → implementation status/issues → PM tracking | Planned mechanism; no direct interaction claimed | PM + ML Engineering | High
CO-04 | PM ↔ Generative AI | Monitor Knowledge Base dependency, prototype progress and safety testing | Knowledge Base → prototype/test evidence → PM tracking | Planned mechanism; no direct interaction claimed | PM + Generative AI | High
CO-05 | Cross-workstream integration | Track handoffs between analysis, modelling, implementation and testing | Milestone outputs → dependent-workstream readiness → PM tracking | Planned mechanism; no direct interaction claimed | PM + All Workstreams | High