## High-Level Project Timeline
HealthConnect Clinic — High-Level Project Timeline
Project: HealthConnect Clinic Experience Lab
Track: Project Management
Project: Improving Patient Appointment Attendance and Healthcare Support Using Data and AI
Planning basis: Relative project weeks, because the assignment does not provide official calendar dates.
WBS ID | Activity / Work Package | Primary Track | Start | End | Duration | Dependency | Deliverable / Milestone | Status
1 | Problem Understanding | All Tracks | Week 4 | Week 4 | 1 week | Project initiation | Problem definition and project foundation | Complete
1.1 | Project Initiation & Planning | Project Management | Week 4 | Week 4 | 1 week | 1 | Project Initiation Package | Complete
1.1.1 | Project Charter | Project Management | Week 4 | Week 4 | 1 week | 1.1 | Project Brief / Charter | Complete
1.1.2 | Scope Definition | Project Management | Week 4 | Week 4 | 1 week | 1.1.1 | Scope Statement | Complete
1.1.3 | Stakeholder Identification | Project Management | Week 4 | Week 4 | 1 week | 1.1.1 | Stakeholder Register | Complete
1.1.4 | WBS Development | Project Management | Week 4 | Week 4 | 1 week | 1.1.2 | Approved WBS | Complete
1.2 | Resource & Data Review | All Tracks | Week 4 | Week 5 | 2 weeks | 1.1 | Resource review findings | Planned
1.3 | Initial Risk & Dependency Identification | Project Management | Week 4 | Week 5 | 2 weeks | 1.1 | Risk & Dependency Register | Planned
2 | Analysis and Solution Design | All Tracks | Week 5 | Week 6 | 2 weeks | 1 | Analysis and solution design outputs | Planned
2.1 | Appointment Attendance Analysis | Data Analytics | Week 5 | Week 6 | 2 weeks | 1.2.1 | Analysis findings | Planned
2.2 | No-Show Prediction Problem Definition | Data Science | Week 5 | Week 6 | 2 weeks | 2.1.1 | ML problem definition | Planned
2.3 | AI Assistant Solution Design | Generative AI | Week 5 | Week 6 | 2 weeks | 1.2.3 | AI Assistant Design | Planned
2.4 | ML System Design | ML Engineering | Week 5 | Week 6 | 2 weeks | 2.2 | ML System Design Document | Planned
2.5 | Integrated Solution Planning | Project Management / All Tracks | Week 6 | Week 6 | 1 week | 2.1–2.4 | Integrated solution plan | Planned
3 | Development | Technical Tracks | Week 7 | Week 9 | 3 weeks | 2 | Working solution components / prototypes | Planned
3.1 | Data Preparation | Data Analytics / Data Science | Week 7 | Week 8 | 2 weeks | 2.1 | Prepared analytical dataset | Planned
3.2 | Analytics Development | Data Analytics | Week 8 | Week 9 | 2 weeks | 3.1 | Analysis outputs | Planned
3.3 | Model Development | Data Science / ML Engineering | Week 8 | Week 9 | 2 weeks | 2.2, 3.1 | Model prototype | Planned
3.4 | AI Assistant Prototype | Generative AI / ML Engineering | Week 8 | Week 9 | 2 weeks | 2.3 | AI assistant prototype | Planned
3.5 | Project Monitoring & Coordination | Project Management | Week 7 | Week 9 | 3 weeks | 3.1–3.4 | Updated project controls | Planned
4 | Testing and Refinement | All Tracks | Week 10 | Week 11 | 2 weeks | 3 | Testing and refinement results | Planned
4.1 | Solution Testing | Relevant Tracks | Week 10 | Week 10 | 1 week | 3.2–3.4 | Test results | Planned
4.2 | AI Safety & Scope Testing | Generative AI | Week 10 | Week 10 | 1 week | 3.4 | AI safety test results | Planned
4.3 | Issue Resolution & Refinement | All Tracks | Week 10 | Week 11 | 2 weeks | 4.1–4.2 | Refined solution outputs | Planned
4.4 | Project Review | Project Management | Week 11 | Week 11 | 1 week | 4.3 | Project readiness review | Planned
5 | Final Presentation | All Tracks | Week 12 | Week 12 | 1 week | 4 | Final project presentation | Planned
5.1 | Final Findings & Recommendations | All Tracks | Week 12 | Week 12 | 1 week | 4.4 | Final findings and recommendations | Planned
5.2 | Final Documentation | Project Management / All Tracks | Week 12 | Week 12 | 1 week | 5.1 | Final project documentation | Planned
5.3 | Final Presentation | All Tracks | Week 12 | Week 12 | 1 week | 5.2 | Final presentation | Planned
Key milestones
Milestone | Target | Owner | Purpose
Week 4 Foundation Complete | End of Week 4 | Project Management | Confirm scope, stakeholders, WBS and initial project controls
Solution Design Complete | End of Week 6 | All Tracks | Confirm analysis, ML, AI and integrated solution approach
Development Complete | End of Week 9 | Technical Tracks | Complete planned prototypes and technical outputs
Testing & Refinement Complete | End of Week 11 | All Tracks | Validate outputs and resolve identified issues
Final Presentation Ready | End of Week 12 | All Tracks | Consolidate documentation, findings and presentation