HEALTHCONNECT CLINIC

Project Brief / Charter

Improving Patient Appointment Attendance and Healthcare Support Using Data and AI

| Project | HealthConnect Clinic Experience Lab | Track | Project Management |
| --- | --- | --- | --- |
| Version | 1.0 | Project Stage | Initiation / Problem Understanding |
| Prepared by | Project Management Intern | Date | August 2026 |
| Status | Initial | Next Review | Following Week 4 planning activities |

# 1. Project Background

HealthConnect Clinic is a fictional outpatient healthcare provider that manages appointment-based services for adult patients. The clinic aims to provide accessible, organised, and patient centered care. The clinic is experiencing operational and patient-support challenges, including missed scheduled appointments, difficulty understanding factors associated with appointment no-shows, inefficient use of appointment slots, repetitive patient enquiries, and the need to improve patient engagement and administrative support.

The project will explore how data, machine learning, and Generative AI can support better decision-making and improve the patient support experience.

# 2. Business Problem

HealthConnect Clinic needs to better understand and address appointment non-attendance while improving the efficiency of appointment related administrative support.

Understand patterns associated with missed appointments.

Support better decision making around appointment attendance.

Improve the use of available appointment slots.

Reduce repetitive appointment-related enquiries.

Improve patient engagement and administrative support.

# 3. Project Purpose

The purpose of the HealthConnect project is to establish and develop data and AI supported approach that can help the clinic reduce missed appointments and improve the patient support experience. The project will bring together Project Management, Data Analytics, Data Science, Machine Learning Engineering, and Generative AI perspectives.

# 4. Central Project Question

How can HealthConnect Clinic use data and AI to reduce missed appointments and improve the patient support experience?

# 5. Project Objectives

Understand the factors and patterns associated with missed appointments.

Use appointment data to support evidence based decision making.

Explore an appropriate approach for predicting or identifying appointment no show risk.

Explore how AI can support appointment related administrative and informational enquiries.

Establish appropriate safety boundaries for AI supported patient assistance.

Develop and evaluate proposed solutions before final presentation.

Improve understanding of how data and AI can support appointment attendance and patient support.

# 6. Initial Success Criteria

A clear understanding of the appointment attendance problem is established.

Useful analysis of appointment and no-show patterns is produced.

An appropriate proposed data/AI solution is developed.

A clearly defined approach for improving administrative patient support is provided.

Generative AI outputs remain within the approved HealthConnect Knowledge Base.

Key risks, dependencies, assumptions, and limitations are identified.

Project outputs are documented and professionally presented.

Recommendations are supported by project findings.

# 7. High-Level Scope

## 7.1 In Scope

Understanding the appointment attendance and no-show problem.

Reviewing and analysing the available appointment data.

Identifying relevant patterns and factors.

Exploring data and machine learning approaches related to appointment attendance.

Designing an AI supported administrative and informational assistant.

Establishing AI safety boundaries and escalation procedures.

Testing and refining proposed solutions.

Project planning, coordination, documentation, and final presentation.

## 7.2 Out of Scope

Medical diagnosis.

Prescribing or recommending medication or treatment.

Providing personalized clinical advice.

Replacing qualified healthcare professionals.

Inventing clinic policies, prices, appointment availability, or medical information.

Providing emergency medical advice beyond directing users to appropriate emergency help.

# 8. Key Project Deliverables

- Project initiation and planning documentation.

Appointment data assessment and analysis.

Identification of appointment attendance/no-show patterns.

Proposed data or machine learning solution.

Healthcare Information Assistant design.

Solution development/prototyping.

Testing and refinement.

Final project findings and recommendations.

Final project presentation.

# 9. Key Stakeholder Groups

HealthConnect Clinic management.

Clinic reception and administrative staff.

Healthcare/support staff.

Patients.

Project Management team.

Data Analytics team.

Data Science team.

Machine Learning Engineering team.

Generative AI team.

Project sponsor/mentor.

# 10. Key Assumptions

The provided HealthConnect resources are the approved project resources.

The appointment dataset can support initial investigation of appointment attendance.

Different project tracks will contribute their respective expertise to the shared project.

Project activities will progress through problem understanding, analysis and solution design, development, testing and refinement, and final presentation.

The HealthConnect Knowledge Base will be used as the approved information source for the Healthcare Information Assistant.

Project outputs will remain within the fictional HealthConnect project environment.

# 11. Key Constraints

The project uses fictional and anonymised project resources.

The available data may have limitations that affect analysis and solution development.

The project has defined weekly deadlines and deliverables.

AI functionality must remain within the approved Knowledge Base.

Medical and clinical advice is outside the approved AI scope.

The final solution may depend on the quality and availability of project data and technical resources.

# 12. Major Dependencies

Availability and quality of the HealthConnect appointment dataset.

Understanding of the HealthConnect Data Dictionary.

Availability of approved clinic information in the Knowledge Base.

Timely completion of work by the different project tracks.

Coordination between Project Management, Data Analytics, Data Science, Machine Learning Engineering, and Generative AI teams.

Stakeholder feedback during solution development and testing.

Availability of appropriate tools and technical resources.

# 13. Initial Project Risks

| Risk | Potential Impact | Initial Response |
| --- | --- | --- |
| Poor or incomplete data quality | Could affect analysis and project decisions | Conduct early data-quality assessment |
| Delays between project workstreams | Could delay dependent activities | Establish milestones and regular communication |
| Unclear project requirements | Could lead to rework | Confirm requirements and scope early |
| AI producing unsupported information | Could create safety and accuracy concerns | Restrict AI to the approved Knowledge Base |
| Technical limitations | Could affect solution development | Identify technical dependencies early |
| Insufficient stakeholder feedback | Could reduce solution relevance | Establish regular review and feedback points |
| Scope expansion | Could increase workload and delay delivery | Maintain clear scope and change-control approach |

# 14. Project Governance and Management Approach

The Project Management track will establish the structure required to coordinate the HealthConnect project effectively.

Define project scope and objectives.

Break the project into manageable workstreams.

Establish responsibilities and dependencies.

Develop a high-level project timeline.

Monitor project risks and issues.

Maintain communication across project teams.

Track progress against planned milestones.

Support coordination between the different professional tracks.

# 15. High-Level Project Phases

| Project Phase | Purpose |
| --- | --- |
| Phase 1 — Problem Understanding | Understand the business problem, resources, requirements, stakeholders, assumptions, and constraints. |
| Phase 2 — Analysis and Solution Design | Analyse relevant information and define appropriate data, AI, and project solutions. |
| Phase 3 — Development | Develop or prototype the proposed solutions. |
| Phase 4 — Testing and Refinement | Evaluate outputs, identify issues, refine solutions, and confirm alignment with requirements. |
| Phase 5 — Final Presentation | Present the project's findings, solution approach, outputs, limitations, and recommendations. |

# 16. Project Management Track Responsibility

The Project Management track is responsible for establishing the initial structure required to manage the HealthConnect project effectively.

Project scope and objectives.

Stakeholder identification and engagement.

Work Breakdown Structure.

High-level scheduling.

Risk and dependency management.

Communication planning.

Project documentation and coordination.

# 17. Initial Project Focus

The immediate focus is to establish a clear project foundation before detailed analysis and development begin.

- Define detailed project scope.

Develop the stakeholder register.

Create the Work Breakdown Structure.

Establish the high-level project timeline.

Develop the risk and dependency register.

Establish the project communication approach.