HEALTHCONNECT CLINIC

Project Scope Statement

Improving Patient Appointment Attendance and Healthcare Support Using Data and AI

| Project | HealthConnect Clinic Experience Lab | Track | Project Management |
| --- | --- | --- | --- |
| Version | 1.0 | Project Stage | Initiation / Problem Understanding |
| Prepared by | Project Management Intern | Date | August 2026 |
| Status | Initial | Next Deliverable | Stakeholder Register |

# 1. Scope Overview

The HealthConnect project will explore how data, machine learning, and Generative AI can support HealthConnect Clinic in reducing missed appointments and improving the patient support experience. The project will coordinate multiple professional tracks to understand the business problem, analyse relevant appointment information, design appropriate solutions, develop or prototype those solutions, test and refine them, and present the final findings. The project scope is focused on appointment attendance, administrative support, data/AI-enabled decision-making, and project coordination.

# 2. Scope Objectives

Understand the business problem surrounding missed appointments.

Identify relevant appointment attendance patterns and factors.

Explore data-driven approaches for supporting appointment attendance.

Explore an appropriate machine learning approach for appointment no-show prediction were supported by the available data.

Design an AI-supported administrative and informational assistant.

Establish appropriate AI safety and escalation boundaries.

Coordinate the activities of the different project workstreams.

Test and refine the proposed solutions.

Produce documented findings and recommendations.

# 3. In-Scope Activities

## 3.1 Project Management

Project initiation and planning.

Scope definition and control.

Stakeholder identification and management.

Work Breakdown Structure development.

High-level scheduling.

Risk and dependency management.

Communication planning.

Progress monitoring.

Project documentation.

Coordination across project workstreams.

## 3.2 Data and Analytics

Reviewing the available appointment dataset.

Understanding relevant variables and data structure.

Assessing data quality.

Investigating appointment attendance and no-show patterns.

Identifying business questions relevant to the project.

Supporting evidence-based project decisions.

## 3.3 Data Science / Machine Learning

Defining the appointment no-show prediction problem.

Identifying an appropriate target variable.

Identifying potential predictive features.

Developing an initial modelling approach.

Evaluating the proposed approach during later project stages.

## 3.4 Generative AI

The project will include the design and potential development of an administrative and informational Healthcare Information Assistant.

Supported areas may include:

Clinic opening hours.

Clinic locations.

Available services.

Appointment procedures.

Rescheduling and cancellation procedures.

Late arrival procedures.

Approved administrative check-in information.

Directing users to appropriate clinic support when information is unavailable or outside scope.

# 4. Out-of-Scope Activities

Diagnosing medical conditions.

Prescribing or recommending medication.

Recommending medical treatment.

Interpreting symptoms as a clinical conclusion.

Providing personalised clinical advice.

Replacing doctors, nurses, or other qualified healthcare professionals.

Providing emergency medical advice beyond directing users to appropriate emergency help.

Inventing clinic policies or procedures.

Inventing prices, insurance coverage, discounts, or payment arrangements.

Inventing appointment availability.

Providing medical information that is not supported by the approved project resources.

# 5. Key Project Deliverables

- Project initiation and planning documentation.

Appointment data assessment and analysis.

Identification of appointment attendance and no-show patterns.

Proposed data or machine learning solution.

Healthcare Information Assistant design.

Solution prototype or development output, where applicable.

Testing and refinement results.

Final findings and recommendations.

Final project presentation.

# 6. Project Boundaries

## 6.1 Data Boundary

The project will use the HealthConnect project resources provided for the Experience Lab. Any conclusions will be limited by the quality, completeness, and suitability of the available data.

## 6.2 AI Boundary

The Healthcare Information Assistant will operate only within the approved HealthConnect Knowledge Base and defined safety rules.

## 6.3 Clinical Boundary

The project does not provide clinical diagnosis, treatment, medication recommendations, or personalised medical advice.

## 6.4 Project Boundary

The Project Management track will coordinate planning, scope, stakeholders, schedule, risks, dependencies, communication, and documentation. It will not replace the specialist responsibilities of the Data Analytics, Data Science, Machine Learning Engineering, or Generative AI tracks.

## 6.5 Project Stage Boundary

Week 4 establishes the project foundation. Detailed analysis, development, testing, and final solution evaluation will occur during later project stages.

# 7. Acceptance Criteria

The project objectives and boundaries are clearly documented.

Major project workstreams and deliverables are identified.

Stakeholders are identified and their engagement needs are documented.

The project has a structured Work Breakdown Structure.

Major project milestones and dependencies are identified.

Major risks are documented with initial responses.

A communication approach is established.

Data and AI activities remain aligned with the approved project scope.

AI-related outputs remain within the approved Knowledge Base and safety boundaries.

Final project outputs address the central project question.

# 8. Key Assumptions

The HealthConnect project resources provided by AnalystLab Africa are the approved project resources.

The available appointment data is sufficient for an initial investigation of appointment attendance.

The different professional tracks will contribute to the shared project according to their assigned responsibilities.

Project activities will progress through the defined project stages.

Stakeholder feedback will be available when required.

Technical resources required for later development activities will be available where applicable.

# 9. Key Constraints

The project uses fictional and anonymised resources.

Data quality may limit the reliability of analysis or modelling.

Weekly internship deadlines may limit the amount of work completed during each stage.

The AI assistant must remain within the approved Knowledge Base.

Clinical and medical decision-making is outside the project's approved scope.

Technical limitations may affect development or implementation.

Changes to project requirements may require additional review and approval.

# 10. Scope Change Control

Any significant change to the agreed project scope should be reviewed before implementation.

A proposed scope change should be assessed based on:

Impact on project objectives.

Impact on project timeline.

Impact on available resources.

Impact on project risks.

Impact on other workstreams.

Impact on AI safety and approved project boundaries.

Whether the change is supported by the available project resources.

Changes that expand the project beyond its approved administrative, analytical, data, and AI scope should not be implemented without appropriate review.

# 11. Scope Management Approach

Review deliverables against the approved scope.

Track changes and potential scope creep.

Monitor dependencies between workstreams.

Review risks that may affect scope.

Communicate changes to relevant stakeholders.

Ensure project activities remain aligned with the central project question.

# 12. Scope Statement Summary

The HealthConnect project will focus on using project management, data, machine learning, and Generative AI approaches to investigate missed appointments and improve administrative patient support. The project will not extend into clinical diagnosis, treatment, medication recommendations, or unsupported medical information. The Project Management track will provide the structure needed to coordinate the work through problem understanding, analysis and solution design, development, testing and refinement, and final presentation.