HEALTHCONNECT CLINIC

WEEK 4 PROJECT SUMMARY

Project: HealthConnect Clinic Experience Lab

Project Title: Improving Patient Appointment Attendance and Healthcare Support Using Data and AI

Professional Track: Project Management

Week: Week 4

Version: 1.0

# 1. Specific Problem Addressed:

The Project Management track is responsible for establishing the initial structure required to effectively plan, coordinate, and monitor the HealthConnect project.

The main focus is to define the project scope and objectives, identify key stakeholders and workstreams, break the project into manageable activities, establish a high-level timeline, identify major risks and dependencies, and develop an effective communication approach.

This structure will help coordinate the different professional tracks and ensure that the project remains aligned with the central objective of reducing missed appointments and improving the patient support experience.

# 2. Resources Used:

The Week 4 project work was based on the resources and guidance provided by the HealthConnect Experience Lab, including:

- HealthConnect business scenario and central project question.

- HealthConnect Appointment Dataset.

- HealthConnect Data Dictionary.

- HealthConnect Clinic Knowledge Base.

- Week 4 Project Management assignment requirements.

- Project Management tools recommended in the assignment, including Microsoft Excel, Microsoft Word, PowerPoint, Trello, Notion, and Jira or similar project management tools.

# 3. Key Observations from Week 4:

The following observations were made during the project initiation stage:

- HealthConnect is a cross-functional project involving Project Management, Data Analytics, Data Science, Machine Learning Engineering, and Generative AI.

- The project addresses several related challenges, including appointment no-shows, inefficient appointment-slot utilisation, repetitive patient enquiries, and the need to improve patient engagement and administrative support.

- The different professional tracks are interconnected, meaning that delays or incomplete outputs from one workstream may affect other workstreams.

- Week 4 is primarily focused on understanding the problem, defining the project structure, and preparing for the next stages rather than completing the final solution.

- Clear project scope, stakeholder coordination, risk management, dependency tracking, and communication will be important for maintaining project alignment.

# 4. Proposed Approach:

The proposed Project Management approach is to manage the HealthConnect project through clearly defined workstreams and progressive project stages.

The Work Breakdown Structure will provide the foundation for organising project activities and

deliverables. The stakeholder register will help clarify stakeholder interests, influence, and responsibilities, while the risk and dependency register will support proactive identification and management of potential project challenges.

The communication approach will establish how project information, progress updates, risks, decisions, and important changes are communicated to the relevant team members and stakeholders.

Project progress will be monitored against agreed activities and milestones, while significant risks, issues, dependencies, and decisions will be documented and escalated when necessary.

# 5. Key Considerations:

Several factors may affect the successful delivery of the HealthConnect project:

- Data quality or incomplete information may affect activities that depend on the appointment dataset and supporting resources.

- Changes to the agreed project scope may create additional work or affect the project timeline.

- Dependencies between professional tracks may cause delays if prerequisite activities are not completed on time.

- The limited internship timeframe means that project activities and deliverables will need to be properly prioritised.

- The Generative AI component must remain within the approved scope and safety boundaries of the HealthConnect Clinic Knowledge Base.

- Poor communication or unclear responsibilities could result in duplicated work, missed tasks, or project delays.

- Availability of required tools, resources, and team members may affect project progress.

# 6. Proposed Focus for Week 5:

The proposed focus for Week 5 is to move from project initiation and problem understanding into analysis and solution design.

From the Project Management perspective, the priorities will be to:

- Monitor progress against the project plan and timeline.

- Coordinate activities across the different professional tracks.

- Review and update project risks and dependencies.

- Support clarification of project requirements where necessary.

- Monitor workstream deliverables and dependencies.

- Ensure that planned activities remain aligned with the approved project scope and objectives.

- Identify and escalate significant issues that could affect project progress.

# 7. Week 4 Conclusion:

Week 4 established the project management foundation for the HealthConnect Experience Lab.

The project scope, stakeholders, work breakdown structure, timeline, risks, dependencies, and communication approach provide a structured framework for managing the project as it progresses.

This foundation will support effective coordination between the different professional tracks and provide a basis for moving into the Analysis and Solution Design stage in Week 5.