## WBS
HEALTHCONNECT CLINIC — WORK BREAKDOWN STRUCTURE
Improving Patient Appointment Attendance and Healthcare Support Using Data and AI
Project | HealthConnect Clinic Experience Lab | Track | Project Management
Version | 1 | Project Stage | Initiation / Problem Understanding
Prepared by | Project Management Intern | Date | August 2026
WBS ID | Workstream / Activity | Description / Work Package | Primary Track | Deliverable / Output | Dependency | Level
1.0 | Problem Understanding | Establish the business problem, project requirements, resources, stakeholders, assumptions and constraints. | All Tracks | Approved problem definition and project foundation | Project initiation | 1
1.1 | Project Initiation & Planning | Define project charter, scope, stakeholders, governance and initial project controls. | Project Management | Project Initiation Package | 1.0 | 2
1.1.1 | Project Charter | Document background, business problem, purpose, objectives and success criteria. | Project Management | Project Brief / Charter | 1.1 | 3
1.1.2 | Scope Definition | Define in-scope and out-of-scope activities, boundaries and acceptance criteria. | Project Management | Scope Statement | 1.1.1 | 3
1.1.3 | Stakeholder Identification | Identify stakeholders, influence, interest, expectations and engagement needs. | Project Management | Stakeholder Register | 1.1.1 | 3
1.1.4 | WBS Development | Break the project into manageable workstreams and work packages. | Project Management | Approved WBS | 1.1.2 | 3
1.2 | Resource & Data Review | Review project resources relevant to each professional track. | All Tracks | Resource review findings | 1.1 | 2
1.2.1 | Appointment Data Review | Review the available appointment dataset and identify relevant project information. | Data Analytics / Data Science | Dataset understanding | 1.2 | 3
1.2.2 | Data Dictionary Review | Review variable definitions and data structure. | Data Analytics / Data Science | Data dictionary understanding | 1.2 | 3
1.2.3 | Clinic Knowledge Base Review | Review approved clinic information and AI scope/safety boundaries. | Generative AI | Approved AI information boundaries | 1.2 | 3
1.3 | Initial Risk & Dependency Identification | Identify major risks, assumptions, limitations and dependencies affecting the project. | Project Management | Initial Risk & Dependency Register | 1.1 | 2
2.0 | Analysis and Solution Design | Analyse relevant information and define appropriate data, machine learning and AI solution approaches. | All Tracks | Analysis and solution design outputs | 1.0 | 1
2.1 | Appointment Attendance Analysis | Investigate appointment attendance and no-show patterns. | Data Analytics | Analysis findings | 1.2.1 | 2
2.1.1 | Data Quality Assessment | Assess completeness, consistency and suitability of available appointment data. | Data Analytics | Data quality assessment | 2.1 | 3
2.1.2 | Business Questions & KPIs | Define business questions and potential KPIs relevant to attendance and no-shows. | Data Analytics | Business questions and KPI definitions | 2.1.1 | 3
2.2 | No-Show Prediction Problem Definition | Define the machine learning problem and assess data suitability. | Data Science | ML problem definition | 2.1.1 | 2
2.2.1 | Target & Feature Definition | Identify proposed target variable and potential input features. | Data Science | Target and feature specification | 2.2 | 3
2.2.2 | Modelling Approach | Define initial modelling approach and modelling considerations. | Data Science | Initial modelling approach | 2.2.1 | 3
2.3 | AI Assistant Solution Design | Define an administrative and informational Healthcare Information Assistant within approved scope. | Generative AI | AI Assistant Design | 1.2.3 | 2
2.3.1 | Use Cases & Supported Requests | Define intended users and supported administrative/informational requests. | Generative AI | Use-case definition | 2.3 | 3
2.3.2 | Safety & Escalation Design | Define out-of-scope requests, safety boundaries and escalation approach. | Generative AI | Safety and escalation design | 2.3.1 | 3
2.4 | ML System Design | Define expected inputs/outputs, workflow, architecture and technical dependencies. | Machine Learning Engineering | ML System Design Document | 2.2 | 2
2.5 | Integrated Solution Planning | Align analytical, ML, AI and project-management outputs into a coherent solution plan. | Project Management / All Tracks | Integrated solution plan | 2.1–2.4 | 2
3.0 | Development | Develop or prototype the proposed data, machine learning and AI solutions. | Technical Tracks | Working solution components / prototypes | 2.0 | 1
3.1 | Data Preparation | Prepare and transform project data for approved analytical or modelling activities. | Data Analytics / Data Science | Prepared analytical dataset | 2.1 | 2
3.2 | Analytics Development | Develop analysis outputs and supporting visualisations where applicable. | Data Analytics | Analysis outputs | 3.1 | 2
3.3 | Model Development | Develop and train the proposed no-show prediction model where supported by the data. | Data Science / ML Engineering | Model prototype | 2.2, 3.1 | 2
3.4 | AI Assistant Prototype | Develop/prototype the administrative and informational assistant within approved scope. | Generative AI / ML Engineering | AI assistant prototype | 2.3 | 2
3.5 | Project Monitoring & Coordination | Track progress, risks, dependencies, issues and workstream coordination during development. | Project Management | Updated project controls | 3.1–3.4 | 2
4.0 | Testing and Refinement | Evaluate outputs, identify issues, refine solutions and confirm alignment with requirements. | All Tracks | Testing and refinement results | 3.0 | 1
4.1 | Solution Testing | Test analytical, modelling and AI outputs against defined requirements. | Relevant Tracks | Test results | 3.2–3.4 | 2
4.2 | AI Safety & Scope Testing | Check assistant behaviour against approved Knowledge Base and escalation rules. | Generative AI | AI safety test results | 3.4 | 2
4.3 | Issue Resolution & Refinement | Address identified issues and refine project outputs. | All Tracks | Refined solution outputs | 4.1–4.2 | 2
4.4 | Project Review | Review scope, risks, dependencies, deliverables and readiness for final presentation. | Project Management | Project readiness review | 4.3 | 2
5.0 | Final Presentation | Consolidate findings, solution approach, limitations and recommendations for final presentation. | All Tracks | Final project presentation | 4.0 | 1
5.1 | Final Findings & Recommendations | Consolidate evidence, findings, limitations and recommendations. | All Tracks | Final findings and recommendations | 4.4 | 2
5.2 | Final Documentation | Organise final project documentation and supporting files. | Project Management / All Tracks | Final project documentation | 5.1 | 2
5.3 | Final Presentation | Prepare and deliver the final HealthConnect project presentation. | All Tracks | Final presentation | 5.2 | 2

## WBS Notes
WBS Notes & Usage
Item | Guidance
Purpose | The WBS decomposes the HealthConnect project into manageable workstreams and work packages.
Hierarchy | Level 1 represents the five project stages; Level 2 represents major workstreams; Level 3 represents work packages.
Dependency use | Dependencies indicate prerequisite activities and will be used when developing the high-level timeline.
Track alignment | Primary Track identifies the professional track most directly responsible for each work package.
Scope control | Activities outside the approved Scope Statement should not be added without scope review.
Next step | Use this WBS as the foundation for the High-Level Timeline and Risk & Dependency Register.