## Risk Register
HealthConnect — Initial Risk & Dependency Register
Risk Register
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Level | Mitigation / Response | Risk Owner | Status
R001 | Appointment data may contain missing or incomplete records that affect analysis and modelling. | Data | Medium | High | High | Conduct data quality checks and document missing or incomplete fields before analysis. | Data Analytics / Data Science | Open
R002 | Project scope may expand beyond the agreed HealthConnect objectives. | Scope | Medium | High | High | Clearly define in-scope and out-of-scope activities and apply change control. | Project Manager | Open
R003 | Different project tracks may experience delays that affect dependent activities. | Schedule | Medium | High | High | Monitor milestones, dependencies and progress regularly and escalate delays early. | Project Manager | Open
R004 | Team members may have conflicting priorities or limited availability. | Resource | Medium | Medium | Medium | Establish clear responsibilities and maintain regular project communication. | Project Manager | Open
R005 | Dependencies between data, analytics, ML and AI workstreams may cause bottlenecks. | Dependency | Medium | High | High | Maintain a dependency register and identify prerequisite deliverables early. | Project Manager | Open
R006 | The AI assistant may provide information outside the approved clinic knowledge base. | AI / Safety | Low | High | High | Restrict responses to approved information and implement escalation rules. | Generative AI Track | Open
R007 | Project requirements may not be clearly understood by all team members. | Requirements | Medium | Medium | Medium | Document requirements and review them with relevant stakeholders. | Project Manager | Open
R008 | Communication gaps may cause inconsistent understanding of project progress or decisions. | Communication | Medium | Medium | Medium | Establish a communication schedule and document key decisions and updates. | Project Manager | Open
R009 | Technical limitations may affect development or integration of proposed solutions. | Technical | Medium | Medium | Medium | Identify technical dependencies early and maintain alternative approaches where practical. | Technical Tracks | Open
R010 | Project outputs may not be completed within the available internship timeframe. | Schedule | Medium | High | High | Prioritise critical deliverables, monitor progress against milestones and escalate risks early. | Project Manager | Open

## Dependency Register
Dependency Register
Dependency ID | Dependency | Dependent Activity | Dependency Type | Owner | Potential Impact | Status
D001 | Availability and usability of the HealthConnect appointment dataset | Data analysis and modelling | Data | Data Analytics / Data Science | Delayed analysis | Open
D002 | Availability of the HealthConnect Data Dictionary | Data interpretation and analysis | Information | Data Analytics / Data Science | Incorrect interpretation of variables | Open
D003 | Availability of the Clinic Knowledge Base | AI Assistant design and development | Information | Generative AI | AI scope and safety issues | Open
D004 | Completion of project scope and requirements | All workstreams | Project | Project Manager | Scope confusion and rework | Open
D005 | Completion of analysis and solution design | Development activities | Technical / Process | Relevant Tracks | Development delays | Open
D006 | Coordination between professional tracks | Integrated solution | Team | Project Manager | Workstream bottlenecks | Open
D007 | Availability of required tools and project resources | Development and documentation | Technical | Relevant Track Leads | Reduced productivity | Open
D008 | Completion of development activities | Testing and refinement | Process | Technical Tracks | Testing delays | Open