## Info
HealthConnect Week 7 PM Testing & Readiness Tracker
Project: | HealthConnect Clinic Experience Lab
Project Title: | Improving Patient Appointment Attendance and Healthcare Support Using Data and AI
Overall Project Question: | How can HealthConnect Clinic use data and AI to reduce missed appointments and improve the patient support experience?
Track: | Project Management
Week 7 Stage: | Testing → Refinement → End-to-End Validation
Continuity: | Builds directly from Week 6 Integration & Coordination Package; no new project or dataset introduced.
Evidence rule: | Completed / PASS only where actual evidence exists. Pending Evidence where verification is not available. Open for unresolved issues/dependencies. In Progress for active PM coordination.
Verified Week 7 activity: | Data Analytics → Project Management validation of No-Show Rate by Previous No-Show Group.
Verified result: | PASS — dashboard values matched supplied underlying validation values: 43.5%, 54.8%, 68.8%.
Overall readiness: | CONDITIONAL — other technical evidence and end-to-end validation remain pending.
Workbook purpose: | Testing coordination, evidence tracking, issue/dependency management, risks, decisions, timeline and Week 8 readiness.

## Week 7 Testing Plan
Week 7 Testing Plan
Plan Area | Purpose | Status | Evidence/Notes
Testing scope | Coordinate testing across PM, Data Analytics, Data Science, ML Engineering and Generative AI. | In Progress | Verified Data Analytics activity completed; other technical evidence pending.
Testing standard | Use actual evidence to assign status; do not infer technical completion from plans or communication. | Completed | Applied throughout workbook.
Cross-track priority | Complete at least one meaningful cross-track validation activity. | Completed / PASS | Data Analytics → PM validation completed.
Issue management | Log actual findings, owners, status, actions and retest evidence. | In Progress | Validated item closed; technical evidence gaps open.
Readiness gate | Assess component and overall readiness before Week 8 final integration. | In Progress | Overall readiness remains Conditional.

## Testing Activity Tracker
Testing Activity Tracker
Test ID | Component Tested | Testing Objective | Test/Scenario | Expected Result | Actual Result | Pass/Fail | Issue Identified | Action Taken | Retest Result | Track Collaborating | Evidence
T-001 | No-Show Rate by Previous No-Show Group | Verify that the Week 6 finding relating previous no-show history to subsequent no-show rates remains consistent in the underlying Power BI data/calculations. | Review grouped appointment counts and calculated no-show rates against the expected Week 6 values. | 0 previous: 43.5%; 1–2: 54.8%; 3+: 68.8%. | 0 previous: 43.5%; 1–2: 54.8%; 3+: 68.8%. | PASS | No calculation inconsistency identified. | No corrective calculation required; documented validation evidence added. | PASS — output remained consistent after verification. | Data Analytics → Project Management | Power BI/dashboard outputs and supplied underlying validation table; verified Week 7 testing evidence.
T-002 | Project Management testing controls | Confirm that PM testing coordination, issue/dependency tracking and readiness controls are in place for Week 7. | Review testing plan, tracker structure, issue/dependency controls and readiness assessment. | Controls documented and usable for Week 7 coordination. | Pending Evidence | Pending Evidence | No technical completion inferred from planning documentation. | Continue PM coordination and evidence collection. | Pending Evidence | Project Management | Week 7 PM Testing Coordination & Project Readiness Package.
T-003 | Data Science outputs | Verify Data Science component-level outputs before final integration. | Evidence-based review of actual Data Science test/validation outputs. | Actual test evidence available and consistent with agreed requirements. | Pending Evidence | Pending Evidence | Technical evidence not provided. | Obtain and review evidence; record findings and coordinate retest if required. | Pending Evidence | Data Science | Not yet verified.
T-004 | ML Engineering outputs | Verify ML Engineering component-level outputs before final integration. | Evidence-based review of actual ML/model or pipeline validation outputs. | Actual test evidence available and consistent with agreed requirements. | Pending Evidence | Pending Evidence | Technical evidence not provided. | Obtain and review evidence; record findings and coordinate retest if required. | Pending Evidence | ML Engineering | Not yet verified.
T-005 | Generative AI outputs | Verify GenAI component-level outputs, including applicable safety/reliability controls, before final integration. | Evidence-based review of actual GenAI testing/validation outputs. | Actual test evidence available and applicable safety/reliability checks documented. | Pending Evidence | Pending Evidence | Technical evidence not provided. | Obtain and review evidence; record findings and coordinate retest if required. | Pending Evidence | Generative AI | Not yet verified.
T-006 | End-to-End HealthConnect flow | Determine whether integrated project components operate together sufficiently for Week 8 final integration. | Cross-workstream evidence review after component-level testing is available. | End-to-end validation evidence supports final integration readiness. | Pending Evidence | Pending Evidence | Component-level evidence remains incomplete. | Complete outstanding track testing and coordinate end-to-end validation. | Pending Evidence | Project Management + relevant tracks | Not yet verified.

## Integration & Issue Log
Integration & Issue Log
Issue ID | Source/Track | Issue or Finding | Impact | Owner | Status | Action/Resolution | Retest Status | Evidence
I-001 | Data Analytics | Validated no-show rate by previous no-show group matched expected Week 6 finding. | Low / no adverse impact; validation supports carrying the finding forward. | Project Management | Closed | No corrective calculation required; retain validated result in project evidence. | Completed / PASS | Power BI/dashboard outputs and supplied underlying validation table.
I-002 | Data Science | Testing evidence not yet verified. | May delay confirmation of technical readiness and final integration. | Data Science / Project Management | Open | Provide component-level testing/validation evidence and coordinate review. | Pending Evidence | Not yet provided.
I-003 | ML Engineering | Testing evidence not yet verified. | May delay confirmation of technical readiness and final integration. | ML Engineering / Project Management | Open | Provide component-level testing/validation evidence and coordinate review. | Pending Evidence | Not yet provided.
I-004 | Generative AI | Testing evidence not yet verified. | May delay confirmation of technical readiness and applicable AI safety/reliability validation. | Generative AI / Project Management | Open | Provide component-level testing/validation evidence and coordinate review. | Pending Evidence | Not yet provided.
I-005 | Cross-track | Full end-to-end validation evidence is not yet verified. | Overall project readiness cannot yet be confirmed. | Project Management + relevant tracks | Open | Complete remaining component tests, resolve dependencies, then coordinate end-to-end validation. | Pending Evidence | Week 8 readiness gate.

## Issue Resolution
Issue Resolution
Issue ID | Resolution/Closure Detail | Closure Evidence | Retest Outcome | Closure Status
I-001 | Validation confirmed expected grouped no-show rates; no corrective calculation required. | 2,921/1,271/43.5%; 1,986/1,088/54.8%; 93/64/68.8%; total 5,000/2,423/48.5%. | PASS — output remained consistent after verification. | Closed
I-002 | Pending technical evidence. | Not yet provided. | Pending Evidence | Open
I-003 | Pending technical evidence. | Not yet provided. | Pending Evidence | Open
I-004 | Pending technical evidence. | Not yet provided. | Pending Evidence | Open
I-005 | Pending end-to-end validation. | Not yet provided. | Pending Evidence | Open

## Risk & Dependency Register
Risk & Dependency Register
Risk/Dependency ID | Risk/Dependency | Description | Probability | Impact | Owner | Status | Mitigation/Response | Timeframe
R-001 | Data limitations | Data may constrain interpretation of patient attendance patterns or validation scope. | Medium | Medium | Project Management + Data Analytics | Open | Document data limitations and ensure conclusions remain within evidence scope. | Week 7–8
R-002 | Cross-track delays | Outstanding testing evidence from technical tracks could delay integrated readiness. | Medium | High | Project Management + relevant track owners | Open | Track evidence dependencies and escalate overdue evidence through the PM coordination process. | Week 7–8
R-003 | Testing dependencies | Some tests depend on component outputs becoming available before integration-level validation can proceed. | High | High | Project Management | Open | Sequence testing around evidence availability and coordinate retesting where required. | Week 7–8
R-004 | Missing technical evidence | Data Science, ML Engineering and GenAI testing evidence has not been verified in the supplied Week 7 evidence. | High | High | Relevant track owners + Project Management | Open | Obtain, review and log actual evidence before marking those components complete. | Week 7–8
R-005 | Integration dependencies | Component-level validation does not by itself demonstrate full end-to-end readiness. | High | High | Project Management + relevant tracks | Open | Use a final integrated validation gate after component evidence is complete. | Week 8
R-006 | AI safety/reliability | GenAI-related safety/reliability checks require explicit evidence before technical readiness is confirmed. | Medium | High | Generative AI + Project Management | Open | Verify applicable testing evidence and document any required controls or limitations. | Week 7–8
R-007 | Scope of validation | A passed Data Analytics KPI validation supports that KPI only and should not be generalized to all project components. | Low | High | Project Management | Open | Maintain evidence-based status language and conditional overall readiness. | Week 7–8

## Decision Log
Decision Log
Decision ID | Decision | Reason/Rationale | Status
D-001 | Use evidence-based testing statuses throughout Week 7. | Prevents plans or communications from being treated as proof of technical completion. | Approved
D-002 | Record the Data Analytics → PM validation as completed/PASS because actual evidence was received and values matched. | The supplied underlying validation output confirmed the expected 43.5%, 54.8% and 68.8% rates. | Approved
D-003 | Do not invent an issue where the Data Analytics test passed. | The validation identified no calculation inconsistency and required no corrective calculation. | Approved
D-004 | Keep Data Science, ML Engineering and GenAI readiness conditional until actual testing evidence is verified. | No technical test evidence for those tracks was supplied for Week 7. | Approved
D-005 | Treat outstanding testing dependencies as open before Week 8 final integration. | End-to-end readiness cannot be established from a single component-level validation. | Approved

## Cross-Track Testing
Cross-Track Testing
Activity ID | Track Collaborated With | Project Dependency | Component/Output Tested | Information/Output Received | Testing Activity Completed | Finding Identified | Refinement/Action Taken | Retest Result | What Changed | Evidence | Contribution to HealthConnect
CT-001 | Data Analytics → Project Management | Previous no-show history is a project dependency because the Week 6 finding may inform coordination of no-show reduction work and validation evidence. | No-Show Rate by Previous No-Show Group | Week 5 analysis and Week 6 integrated finding; Week 7 underlying Power BI validation output. | Testing activity completed: compared expected grouped no-show rates with underlying counts/calculations. | Finding remained supported; no calculation inconsistency identified. | No corrective calculation. Documented validation evidence and carried the finding forward. | PASS — output remained consistent after verification. | No numerical change; added documented validation evidence. | Power BI/dashboard outputs plus underlying validation table: 2,921/1,271/43.5%; 1,986/1,088/54.8%; 93/64/68.8%; total 5,000/2,423/48.5%. | Supports evidence-based coordination of the no-show reduction objective and establishes a verified KPI validation point.
CT-002 | Data Science → Project Management | Component readiness requires actual testing evidence. | Data Science testing outputs | Pending Evidence | Not yet verified. | Pending Evidence | Pending Evidence | Pending Evidence | No change recorded. | Not yet provided. | Needed before final integration readiness can be assessed.
CT-003 | ML Engineering → Project Management | Component readiness requires actual testing evidence. | ML Engineering testing outputs | Pending Evidence | Not yet verified. | Pending Evidence | Pending Evidence | Pending Evidence | No change recorded. | Not yet provided. | Needed before final integration readiness can be assessed.
CT-004 | Generative AI → Project Management | Component readiness and applicable safety/reliability checks require actual testing evidence. | GenAI testing outputs | Pending Evidence | Not yet verified. | Pending Evidence | Pending Evidence | Pending Evidence | No change recorded. | Not yet provided. | Needed before final integration readiness can be assessed.

## Updated Timeline
Updated Timeline
Week | Activity | Purpose/Scope | Owner | Status | Progress/Evidence
Week 7 | Testing | Coordinate planned component and cross-track tests; collect actual evidence. | Project Management + relevant track owners | In Progress | Data Analytics validation completed; other technical evidence pending.
Week 7 | Validation | Verify outputs against expected results and underlying evidence. | Project Management + relevant tracks | In Progress | One verified KPI validation completed; broader validation pending.
Week 7 | Issue identification | Log actual issues, findings and unresolved dependencies. | Project Management | In Progress | Validated item closed; evidence gaps remain open.
Week 7 | Refinement | Apply evidence-based corrections or documentation refinements where needed. | Relevant track owners + Project Management | In Progress | No numerical correction required for tested KPI; evidence documentation refined.
Week 7 | Retesting | Coordinate retesting where issues or refinements require confirmation. | Project Management + relevant tracks | Pending Evidence | No retest correction required for validated KPI; other retests pending evidence.
Week 7 | Readiness assessment | Assess component and overall readiness using verified evidence only. | Project Management | In Progress | Overall readiness remains Conditional.
Week 8 | Final integration | Integrate validated components and complete outstanding end-to-end validation. | Project Management + all relevant tracks | Pending Evidence | Requires closure/verification of outstanding testing dependencies.
Week 8 | Final documentation | Finalize project documentation and presentation evidence. | Project Management + all relevant tracks | Pending Evidence | Depends on final integration evidence.
Week 8 | Final presentation | Present integrated HealthConnect solution and evidence. | Project Team | Pending Evidence | Dependent on final integration readiness.

## Week 8 Readiness
Week 8 Readiness
Component | Readiness Status | Evidence Basis | Required Next Step
Project Management Testing Controls | In Progress | Testing coordination, issue/dependency and readiness controls are documented; actual closure of all testing dependencies remains outstanding. | Complete evidence tracking and final readiness gate.
Data Analytics | Ready for tested KPI / PASS | The tested no-show-rate-by-previous-no-show-group KPI matched the supplied underlying validation values. | Retain evidence and carry validated finding into final integration.
Data Science | Pending Evidence | No actual Week 7 testing evidence supplied. | Obtain and verify evidence.
ML Engineering | Pending Evidence | No actual Week 7 testing evidence supplied. | Obtain and verify evidence.
Generative AI | Pending Evidence | No actual Week 7 testing evidence supplied; applicable safety/reliability evidence also remains unverified. | Obtain and verify evidence.
End-to-End Validation | Pending | Full integrated validation has not been demonstrated by the supplied component-level evidence. | Complete component evidence first, then run end-to-end validation.
Overall Project Readiness | Conditional | One meaningful cross-track validation is PASS, but required technical evidence and end-to-end validation remain outstanding. | Close testing dependencies before Week 8 final integration.

## Outstanding Actions
Outstanding Actions
Action ID | Action | Owner | Status | Target Week | Notes
A-001 | Obtain and review Data Science testing evidence. | Data Science + PM | Open | Week 8 | Required for component readiness assessment.
A-002 | Obtain and review ML Engineering testing evidence. | ML Engineering + PM | Open | Week 8 | Required for component readiness assessment.
A-003 | Obtain and review Generative AI testing and applicable safety/reliability evidence. | Generative AI + PM | Open | Week 8 | Required for component readiness assessment.
A-004 | Track and close outstanding cross-track dependencies. | Project Management | Open | Week 8 | Use issue/dependency log and readiness gate.
A-005 | Coordinate end-to-end validation after component evidence is verified. | Project Management + relevant tracks | Open | Week 8 | Do not infer end-to-end readiness from component tests alone.
A-006 | Finalize Week 8 integrated documentation and presentation evidence. | Project Management + Project Team | Open | Week 8 | Dependent on final integration evidence.