HealthConnect Week 7 Project Management Testing & Validation Report

Testing Coordination & Project Readiness Package

Project: HealthConnect Clinic Experience Lab
Project Title: Improving Patient Appointment Attendance and Healthcare Support Using Data and AI
Track: Project Management
Stage: Week 7 — Testing → Refinement → End-to-End Validation

# Document Control

| Field | Detail |
| --- | --- |
| Document | HealthConnect Week 7 Project Management Testing & Validation Report |
| Project | HealthConnect Clinic Experience Lab |
| Project Question | How can HealthConnect Clinic use data and AI to reduce missed appointments and improve the patient support experience? |
| Track | Project Management |
| Reporting Stage | Week 7 — Testing → Refinement → End-to-End Validation |
| Continuity | Builds directly from the Week 6 Project Integration & Coordination Package. |
| Evidence standard | Only actual supplied/verified evidence is marked Completed/PASS. Missing technical evidence remains Pending Evidence. |
| Overall Week 7 readiness | CONDITIONAL |

# Week 6 → Week 7 Transition

Week 6 established the Workstream Integration Map, Integration/Dependency Register, Integration Readiness tracking, Integration Issue Log, Decision Log, updated timeline, updated risk register, cross-track coordination record, unresolved issues and the Week 7 Testing Coordination Plan. Week 7 operationalizes those controls by moving from integration planning into evidence-based testing, refinement, retesting and readiness assessment.

Week 6 findings were carried forward rather than replaced; no new project or dataset was introduced.

The Data Analytics Week 5 analysis and dashboard findings were already incorporated into PM coordination during Week 6.

Week 7 adds verified validation evidence for one KPI and maintains explicit evidence gaps for technical tracks whose testing outputs were not supplied.

# Week 7 Testing Readiness

Testing was organized around the project workstreams: Project Management, Data Analytics, Data Science, ML Engineering and Generative AI. The PM approach uses a strict evidence rule: plans, communications or expected outputs do not constitute technical completion. This prevents unsupported readiness claims.

| Workstream | Week 7 Status | Evidence Basis |
| --- | --- | --- |
| Project Management | In Progress | Testing controls, issue/dependency tracking and readiness assessment are documented; final closure remains dependent on technical evidence. |
| Data Analytics | Completed / PASS for tested KPI | Actual validation output matched the supplied expected values. |
| Data Science | Pending Evidence | No actual Week 7 technical testing evidence supplied. |
| ML Engineering | Pending Evidence | No actual Week 7 technical testing evidence supplied. |
| Generative AI | Pending Evidence | No actual Week 7 technical testing/safety-reliability evidence supplied. |
| End-to-End Validation | Pending | Full integrated validation has not yet been demonstrated. |

# Verified Cross-Track Testing Activity

Track collaborated with: Data Analytics → Project Management.

| Field | Verified Record |
| --- | --- |
| Project dependency | The previous-no-show-history finding is relevant to coordination of the no-show reduction objective and required validation before being carried forward. |
| Component/output tested | No-Show Rate by Previous No-Show Group. |
| Information/output received | Underlying validation output from the Power BI data/calculations, alongside the expected Week 6 finding. |
| Information/output provided | PM integration and testing evidence record; the validated finding was retained for wider HealthConnect coordination. |
| Testing activity | Compared expected grouped no-show rates with the underlying appointment and no-show counts/calculations. |
| Finding | No calculation inconsistency was identified. |
| Refinement/action | No corrective calculation was required. The refinement was documentation of validation evidence and confirmation that the finding could be carried forward. |
| Retest | Output remained consistent after verification. |
| What changed | No numerical change. The project gained documented validation evidence supporting the tested KPI. |
| Contribution to HealthConnect | Provides a verified evidence point for a no-show-related finding while preventing unsupported generalization to other components. |

# Underlying Data Validation

The verified test used the following underlying validation output:

| Previous No Show Group | Total Appointment | No Show Appointment | No Show Rate |
| --- | --- | --- | --- |
| 0 | 2,921 | 1,271 | 43.5% |
| 1–2 | 1,986 | 1,088 | 54.8% |
| 3+ | 93 | 64 | 68.8% |
| Total | 5,000 | 2,423 | 48.5% |

Expected and actual values were identical: 0 previous no-shows = 43.5%; 1–2 = 54.8%; 3+ = 68.8%. Result: PASS. No calculation correction was required.

# Testing Activity & Issue Management

The Week 7 testing tracker separates verified results from pending evidence. The validated Data Analytics item is closed. Technical evidence gaps for Data Science, ML Engineering and Generative AI remain open because no actual testing outputs were supplied.

| Test ID | Component | Status | Issue/Action | Retest |
| --- | --- | --- | --- | --- |
| T-001 | No-Show Rate by Previous No-Show Group | PASS | No calculation inconsistency identified. No corrective calculation required; documented validation evidence added. | PASS — output remained consistent after verification. |
| T-002 | Project Management testing controls | Pending Evidence | No technical completion inferred from planning documentation. Continue PM coordination and evidence collection. | Pending Evidence |
| T-003 | Data Science outputs | Pending Evidence | Technical evidence not provided. Obtain and review evidence; record findings and coordinate retest if required. | Pending Evidence |
| T-004 | ML Engineering outputs | Pending Evidence | Technical evidence not provided. Obtain and review evidence; record findings and coordinate retest if required. | Pending Evidence |
| T-005 | Generative AI outputs | Pending Evidence | Technical evidence not provided. Obtain and review evidence; record findings and coordinate retest if required. | Pending Evidence |
| T-006 | End-to-End HealthConnect flow | Pending Evidence | Component-level evidence remains incomplete. Complete outstanding track testing and coordinate end-to-end validation. | Pending Evidence |

## Integration & Issue Log

| Issue ID | Source/Track | Finding | Status | Resolution / Next Step |
| --- | --- | --- | --- | --- |
| I-001 | Data Analytics | Validated no-show rate by previous no-show group matched expected Week 6 finding. | Closed | No corrective calculation required; retain validated result in project evidence. |
| I-002 | Data Science | Testing evidence not yet verified. | Open | Provide component-level testing/validation evidence and coordinate review. |
| I-003 | ML Engineering | Testing evidence not yet verified. | Open | Provide component-level testing/validation evidence and coordinate review. |
| I-004 | Generative AI | Testing evidence not yet verified. | Open | Provide component-level testing/validation evidence and coordinate review. |
| I-005 | Cross-track | Full end-to-end validation evidence is not yet verified. | Open | Complete remaining component tests, resolve dependencies, then coordinate end-to-end validation. |

# Updated Risks & Dependencies

| ID | Risk/Dependency | Probability | Impact | Status | Response |
| --- | --- | --- | --- | --- | --- |
| R-001 | Data limitations | Medium | Medium | Open | Document data limitations and ensure conclusions remain within evidence scope. |
| R-002 | Cross-track delays | Medium | High | Open | Track evidence dependencies and escalate overdue evidence through the PM coordination process. |
| R-003 | Testing dependencies | High | High | Open | Sequence testing around evidence availability and coordinate retesting where required. |
| R-004 | Missing technical evidence | High | High | Open | Obtain, review and log actual evidence before marking those components complete. |
| R-005 | Integration dependencies | High | High | Open | Use a final integrated validation gate after component evidence is complete. |
| R-006 | AI safety/reliability | Medium | High | Open | Verify applicable testing evidence and document any required controls or limitations. |
| R-007 | Scope of validation | Low | High | Open | Maintain evidence-based status language and conditional overall readiness. |

A key control is maintaining the distinction between component-level validation and full end-to-end readiness. The Data Analytics PASS validates the tested KPI; it does not establish readiness of the other technical components or the complete HealthConnect flow.

# Major Decisions

| Decision ID | Decision | Rationale | Status |
| --- | --- | --- | --- |
| D-001 | Use evidence-based testing statuses throughout Week 7. | Prevents plans or communications from being treated as proof of technical completion. | Approved |
| D-002 | Record the Data Analytics - PM validation as completed/PASS because actual evidence was received and values matched. | The supplied underlying validation output confirmed the expected 43.5%, 54.8% and 68.8% rates. | Approved |
| D-003 | Do not invent an issue where the Data Analytics test passed. | The validation identified no calculation inconsistency and required no corrective calculation. | Approved |
| D-004 | Keep Data Science, ML Engineering and GenAI readiness conditional until actual testing evidence is verified. | No technical test evidence for those tracks was supplied for Week 7. | Approved |
| D-005 | Treat outstanding testing dependencies as open before Week 8 final integration. | End-to-end readiness cannot be established from a single component-level validation. | Approved |

# Testing Progress / Project Status

Week 7 is progressing from component-level testing toward final readiness assessment. One meaningful cross-track validation is verified as PASS. The remaining technical work is not marked complete because evidence has not been provided. The resulting project status is therefore conditional rather than fully ready.

| Area | Status | Evidence |
| --- | --- | --- |
| Testing coordination | In Progress | Testing plan, trackers, issue/dependency controls and readiness gate established. |
| Verified cross-track validation | Completed / PASS | Data Analytics - PM no-show KPI validation. |
| Issue management | In Progress | Validated item closed; evidence gaps remain open. |
| Retesting | Pending Evidence | No correction was required for the validated KPI; other retests depend on outstanding evidence. |
| End-to-end validation | Pending | Requires completion of component evidence and integrated validation. |
| Overall readiness | Conditional | Not all required testing evidence has been verified. |

# Week 8 Project Readiness Assessment

| Component | Readiness | Evidence Basis | Required Next Step |
| --- | --- | --- | --- |
| Project Management Testing Controls | In Progress | Testing coordination, issue/dependency and readiness controls are documented; actual closure of all testing dependencies remains outstanding. | Complete evidence tracking and final readiness gate. |
| Data Analytics | Ready for tested KPI / PASS | The tested no-show-rate-by-previous-no-show-group KPI matched the supplied underlying validation values. | Retain evidence and carry validated finding into final integration. |
| Data Science | Pending Evidence | No actual Week 7 testing evidence supplied. | Obtain and verify evidence. |
| ML Engineering | Pending Evidence | No actual Week 7 testing evidence supplied. | Obtain and verify evidence. |
| Generative AI | Pending Evidence | No actual Week 7 testing evidence supplied; applicable safety/reliability evidence also remains unverified. | Obtain and verify evidence. |
| End-to-End Validation | Pending | Full integrated validation has not been demonstrated by the supplied component-level evidence. | Complete component evidence first, then run end-to-end validation. |
| Overall Project Readiness | Conditional | One meaningful cross-track validation is PASS, but required technical evidence and end-to-end validation remain outstanding. | Close testing dependencies before Week 8 final integration. |

Overall Project Readiness: CONDITIONAL. The evidence supports readiness for the tested Data Analytics KPI only. Final integration should proceed only after outstanding technical evidence and end-to-end validation have been addressed.

# Outstanding Actions Before Final Integration

| Action | Owner | Status | Target | Purpose |
| --- | --- | --- | --- | --- |
| Obtain and review Data Science testing evidence. | Data Science + PM | Open | Week 8 | Required for component readiness assessment. |
| Obtain and review ML Engineering testing evidence. | ML Engineering + PM | Open | Week 8 | Required for component readiness assessment. |
| Obtain and review Generative AI testing and applicable safety/reliability evidence. | Generative AI + PM | Open | Week 8 | Required for component readiness assessment. |
| Track and close outstanding cross-track dependencies. | Project Management | Open | Week 8 | Use issue/dependency log and readiness gate. |
| Coordinate end-to-end validation after component evidence is verified. | Project Management + relevant tracks | Open | Week 8 | Do not infer end-to-end readiness from component tests alone. |
| Finalize Week 8 integrated documentation and presentation evidence. | Project Management + Project Team | Open | Week 8 | Dependent on final integration evidence. |

# PM Contribution

The Project Management contribution in Week 7 was to turn cross-workstream testing into an evidence-controlled project process: carrying forward Week 6 dependencies, defining test status rules, coordinating a verified Data Analytics validation, recording the result without inventing a defect, maintaining open evidence dependencies, updating risks and decisions, and establishing a conditional Week 8 readiness gate. This supports the HealthConnect objective by improving confidence in validated evidence while keeping unsupported technical claims out of the final integration record.

# Week 7 Conclusion

Week 7 produced a verified PASS for the Data Analytics - Project Management validation of the no-show rate by previous no-show group. The underlying counts and rates matched the expected Week 6 finding, so no corrective calculation was necessary. The main PM outcome is disciplined evidence management: the validated KPI is carried forward, while Data Science, ML Engineering, Generative AI and end-to-end readiness remain Pending Evidence/Conditional until actual testing evidence is verified. The immediate priority for Week 8 is to close those evidence dependencies, coordinate final integration and complete end-to-end validation before final presentation.