## Project Schedule
AI_Power Customer Intelligence Transformation Project
Activity ID | WBS Code | Activity Name | Duration (Days) | Start Date | Finish Date | Predecessor | Assigned Resource | Milestone
1.1 Project Initiation
A01 | 1.1.1 | Develop Project Charter | 2 | 2026-08-17 | 2026-08-18 | _ | Project Manager | No
A02 | 1.1.2 | Identify Stakeholders | 2 | 2026-08-19 | 2026-08-20 | A01 | Project Manager | No
A03 | 1.1.3 | Obtain Project Approval | 1 | 2026-08-21 | 2026-08-21 | A02 | Client Executive Sponsor | Yes
1.2 Project Planning
A04 | 1.2.1 | Develop Project Management Plan | 3 | 2026-08-24 | 2026-08-26 | A03 | Project Manager | No
A05 | 1.2.2 | Create Stakeholder Register | 2 | 2026-08-24 | 2026-08-25 | A03 | Project Manager | No
A06 | 1.2.3 | Develop Risk Register | 2 | 2026-08-24 | 2026-08-25 | A03 | Project Manager | No
A07 | 1.2.4 | Prepare Communication Plan | 2 | 2026-08-26 | 2026-08-27 | A05,A06 | Project Manager | No
1.3 Requirements Analysis
A08 | 1.3.1 | Gather Business Requirements | 5 | 2026-08-28 | 2026-09-03 | A04,A07 | Business Analyst | No
A09 | 1.3.2 | Analyse Customer Data Sources | 4 | 2026-09-04 | 2026-09-09 | A08 | Data Analyst | No
A10 | 1.3.3 | Define Functional Requirements | 3 | 2026-09-04 | 2026-09-08 | A08 | Business Analyst | No
A11 | 1.3.4 | Approve Requirements | 1 | 2026-09-10 | 2026-09-10 | A09,A10 | Client Executive Sponsor | Yes
1.4 Solution Design
A12 | 1.4.1 | Design AI Architecture | 5 | 2026-09-11 | 2026-09-17 | A11 | AI Engineer | No
A13 | 1.4.2 | Design Database Structure | 4 | 2026-09-11 | 2026-09-16 | A11 | Cloud Engineer | No
A14 | 1.4.3 | Quality Review | 2 | 2026-09-18 | 2026-09-21 | A12,A13 | QA Tester | No
A15 | 1.4.4 | Review & Approve Solution Design | 1 | 2026-09-22 | 2026-09-22 | A14 | Project Manager | Yes
1.5 AI Solution Development
A16 | 1.5.1 | Prepare Customer Data | 4 | 2026-09-23 | 2026-09-28 | A13,A15 | Data Analyst | No
A17 | 1.5.2 | Clean Customer Data | 4 | 2026-09-29 | 2026-10-02 | A16 | Data Analyst | No
A18 | 1.5.3 | Develop AI Model | 8 | 2026-10-05 | 2026-10-14 | A17,A15 | AI Engineer | No
A19 | 1.5.4 | Validate AI Model | 4 | 2026-10-15 | 2026-10-20 | A18 | AI Engineer | No
A20 | 1.5.5 | Build Customer Intelligence Dashboard | 5 | 2026-10-15 | 2026-10-21 | A18 | Software Developer | No
A21 | 1.5.6 | Integrate Existing Systems | 5 | 2026-10-22 | 2026-10-28 | A19,A20 | Software Developer | No
1.6 Testing
A22 | 1.6.1 | Unit Testing | 3 | 2026-10-29 | 2026-11-02 | A21 | QA Tester | No
A23 | 1.6.2 | Integration Testing | 4 | 2026-10-03 | 2026-11-06 | A22 | QA Tester | No
A24 | 1.6.3 | User Acceptance Testing | 3 | 2026-11-09 | 2026-11-11 | A23 | End Users | No
A25 | 1.6.4 | Resolve Defects | 3 | 2026-11-09 | 2026-11-11 | A23 | Software Developer | No
A26 | 1.6.5 | Testing Sign-off | 1 | 2026-11-12 | 2026-11-12 | A24,A25 | Project Manager | Yes
1.7 Deployment
A27 | 1.7.1 | Prepare Production Environment | 2 | 2026-11-13 | 2026-11-16 | A26 | Cloud Engineer | No
A28 | 1.7.2 | Deploy AI Solution | 2 | 2026-11-17 | 2026-11-18 | A27 | Cloud Engineer | Yes
A29 | 1.7.3 | Verify Production Deployment | 2 | 2026-11-19 | 2026-11-20 | A28 | QA Tester | No
A30 | 1.7.4 | Conduct User Training | 3 | 2026-11-13 | 2026-11-17 | A26 | Change Management Lead | No
A31 | 1.7.5 | Go-Live Approval | 1 | 2026-11-23 | 2026-11-23 | A29,A30 | Client Executive Sponsor | Yes
1.8 Project Closure
A32 | 1.8.1 | Final Project Review | 1 | 2026-11-24 | 2026-11-24 | A31 | Project Manager | No
A33 | 1.8.2 | Documentment Lessons Learned | 2 | 2026-11-25 | 2026-11-26 | A32 | Project Manager | No
A34 | 1.8.3 | Close Project Documentation | 2 | 2026-11-27 | 2026-11-30 | A33 | Project Manager | No
A35 | 1.8.4 | Obtain Client Sign-off | 1 | 2026-12-01 | 2026-12-01 | A34 | Client Executive Sponsor | Yes
Milestone
Milestone | WBS
Project Approval | 1.1.3
Requirements Approval | 1.3.4
Solution Design Approval | 1.4.4
Testing Sign-off | 1.6.5
Go-Live Approval | 1.7.5
Client Sign-off | 1.8.4

## Gantt Chart
AI_Power Customer Intelligence Transformation Project
Project Gantt Chart
Project Period: 17-Aug-2026 to 01-Dec-2026
Activity ID | Activity Name | Start Date | Duration (Days)
1.1 Project Initiation | time axis 2026-08-17 to 2026-12-01
A01 | Develop Project Charter | 2026-08-17 | 2
A02 | Identify Stakeholders | 2026-08-19 | 2
A03 | Obtain Project Approval | 2026-08-21 | 1
1.2 Project Planning
A04 | Develop Project Management Plan | 2026-08-24 | 3
A05 | Create Stakeholder Register | 2026-08-24 | 2
A06 | Develop Risk Register | 2026-08-24 | 2
A07 | Prepare Communication Plan | 2026-08-26 | 2
1.3 Requirements Analysis
A08 | Gather Business Requirements | 2026-08-28 | 5
A09 | Analyse Customer Data Sources | 2026-09-04 | 4
A10 | Define Functional Requirements | 2026-09-04 | 3
A11 | Approve Requirements | 2026-09-10 | 1
1.4 Solution Design
A12 | Design AI Architecture | 2026-09-11 | 5
A13 | Quality Review | 2026-09-11 | 4
A14 | Design Database Structure | 2026-09-18 | 2
A15 | Review & Approve Solution Design | 2026-09-22 | 1
1.5 AI Solution Development
A16 | Prepare Customer Data | 2026-09-23 | 4
A17 | Clean Customer Data | 2026-09-29 | 4
A18 | Develop AI Model | 2026-10-05 | 8
A19 | Validate AI Model | 2026-10-15 | 4
A20 | Build Customer Intelligence Dashboard | 2026-10-15 | 5
A21 | Integrate Existing Systems | 2026-10-22 | 5
1.6 Testing
A22 | Unit Testing | 2026-10-29 | 3
A23 | Integration Testing | 2026-10-03 | 4
A24 | User Acceptance Testing | 2026-11-09 | 3
A25 | Resolve Defects | 2026-11-09 | 3
A26 | Testing Sign-off | 2026-11-12 | 1
1.7 Deployment
A27 | Prepare Production Environment | 2026-11-13 | 2
A28 | Deploy AI Solution | 2026-11-17 | 2
A29 | Verify Production Deployment | 2026-11-19 | 2
A30 | Conduct User Training | 2026-11-13 | 3
A31 | Go-Live Approval | 2026-11-23 | 1
1.8 Project Closure
A32 | Final Project Review | 2026-11-24 | 1
A33 | Obtain Client Sign-off | 2026-11-25 | 2
A34 | Documentment Lessons Learned | 2026-11-27 | 2
A35 | Close Project | 2026-12-01 | 1

## Critical Path Analysis
AI_Power Customer Intelligence Transformation Project
Critical Path Analysis
Activity ID | Activity Name | Duration | Predecessor | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical?
1.1 Project Initiation
A01 | Develop Project Charter | 2 | _ | 1 | 2 | 1 | 2 | 0 | Critical
A02 | Identify Stakeholders | 2 | A01 | 3 | 4 | 3 | 4 | 0 | Critical
A03 | Obtain Project Approval | 1 | A02 | 5 | 5 | 5 | 5 | 0 | Critical
1.2 Project Planning
A04 | Develop Project Management Plan | 3 | A03 | 6 | 8 | 7 | 9 | 1 | No
A05 | Create Stakeholder Register | 2 | A03 | 6 | 7 | 6 | 7 | 0 | Critical
A06 | Develop Risk Register | 2 | A03 | 6 | 7 | 6 | 7 | 0 | Critical
A07 | Prepare Communication Plan | 2 | A05,A06 | 8 | 9 | 8 | 9 | 0 | Critical
1.3 Requirements Analysis
A08 | Gather Business Requirements | 5 | A04,A07 | 10 | 14 | 10 | 14 | 0 | Critical
A09 | Analyse Customer Data Sources | 4 | A08 | 15 | 18 | 15 | 18 | 0 | Critical
A10 | Define Functional Requirements | 3 | A08 | 15 | 17 | 16 | 18 | 1 | No
A11 | Approve Requirements | 1 | A09,A10 | 19 | 19 | 19 | 19 | 0 | Critical
1.4 Solution Design
A12 | Design AI Architecture | 5 | A11 | 20 | 24 | 20 | 24 | 0 | Critical
A13 | Design Database Structure | 4 | A11 | 20 | 23 | 21 | 24 | 1 | No
A14 | Quality Review | 2 | A12,A13 | 25 | 26 | 25 | 26 | 0 | Critical
A15 | Review & Approve Solution Design | 1 | A14 | 27 | 27 | 27 | 27 | 0 | Critical
1.5 AI Solution Development
A16 | Prepare Customer Data | 4 | A13,A15 | 28 | 31 | 28 | 31 | 0 | Critical
A17 | Clean Customer Data | 4 | A16 | 32 | 35 | 32 | 35 | 0 | Critical
A18 | Develop AI Model | 8 | A17,A15 | 36 | 43 | 36 | 43 | 0 | Critical
A19 | Validate AI Model | 4 | A18 | 44 | 47 | 45 | 48 | 1 | No
A20 | Build Customer Intelligence Dashboard | 5 | A18 | 44 | 48 | 44 | 48 | 0 | Critical
A21 | Integrate Existing Systems | 5 | A19,A20 | 49 | 53 | 49 | 53 | 0 | Critical
1.6 Testing
A22 | Unit Testing | 3 | A21 | 54 | 56 | 54 | 56 | 0 | Critical
A23 | Integration Testing | 4 | A22 | 57 | 60 | 57 | 60 | 0 | Critical
A24 | User Acceptance Testing | 3 | A23 | 61 | 63 | 61 | 63 | 0 | Critical
A25 | Resolve Defects | 3 | A23 | 61 | 63 | 61 | 63 | 0 | Critical
A26 | Testing Sign-off | 1 | A24,A25 | 64 | 64 | 64 | 64 | 0 | Critical
1.7 Deployment
A27 | Prepare Production Environment | 2 | A26 | 65 | 66 | 65 | 66 | 0 | Critical
A28 | Deploy AI Solution | 2 | A27 | 67 | 68 | 67 | 68 | 0 | Critical
A29 | Verify Production Deployment | 2 | A28 | 69 | 70 | 69 | 70 | 0 | Critical
A30 | Conduct User Training | 3 | A26 | 65 | 67 | 68 | 70 | 3 | No
A31 | Go-Live Approval | 1 | A29,A30 | 71 | 71 | 71 | 71 | 0 | Critical
1.8 Project Closure
A32 | Final Project Review | 1 | A31 | 72 | 72 | 72 | 72 | 0 | Critical
A33 | Documentment Lessons Learned | 2 | A32 | 73 | 74 | 73 | 74 | 0 | Critical
A34 | Close Project Documentation | 2 | A33 | 75 | 76 | 75 | 76 | 0 | Critical
A35 | Obtain Client Sign-off | 1 | A34 | 77 | 77 | 77 | 77 | 0 | Critical

## Resource Allocation
AI-Powered Customer Intelligence Transformation Project
Resource Allocation Plan
1. Human Resources
Resource | Responsibility | Assigned Activities | Project Phase | Allocation | Notes
Project Manager | Planning, coordination, monitoring, reporting and project control | A01, A02, A04–A07, A15, A26, A32–A34 | All phases | Throughout project | Coordinates delivery and controls scope, schedule, risks and changes
Client Executive Sponsor | Approvals, business decisions and final sign-off | A03, A11, A31, A35 | Initiation, review and closure | Key milestones | Provides executive decisions and approvals
Business Analyst | Requirements gathering and business requirements | A08, A10 | Requirements | As scheduled | Translates business needs into functional requirements
Data Analyst | Data analysis, preparation and cleaning | A09, A16, A17 | Data preparation | Data phase | Prepares reliable data for modelling and reporting
AI Engineer | AI architecture, model development and validation | A12, A18, A19 | AI development | AI phase | Develops and validates the AI component
Cloud Engineer | Database/cloud architecture and deployment environment | A13, A27, A28 | Technical development and deployment | As scheduled | Supports infrastructure, database and deployment
QA Tester | Quality assurance, testing and production verification | A14, A22, A23, A29 | Testing | Testing phases | Verifies functionality, quality and production readiness
Software Developer | Dashboard development, integration and defect resolution | A20, A21, A25 | Solution development | Development phase | Builds and integrates the customer intelligence solution
End Users | User acceptance testing and feedback | A24 | User acceptance testing | UAT | Validates solution against user needs
Change Management Lead | Training, adoption and change support | A30 | Implementation | As scheduled | Supports user readiness and adoption
2. Software Resources
Resource | Responsibility | Assigned Activities | Project Phase | Allocation | Notes
Microsoft Excel | Schedule, budget, resource planning and reporting | Planning / Control | Project management | As required | Used for project planning and analysis
Microsoft Word | Project documentation and reporting | All documentation | All phases | As required | Used for formal reports and deliverables
PostgreSQL | Database management | Database activities | Data / Database | As scheduled | Supports structured data storage
Python | Data processing and AI development | AI and data activities | AI development | As scheduled | Supports modelling and data processing
Power BI | Customer intelligence dashboard | Dashboard activities | Solution development | As scheduled | Used for data visualization and reporting
Project Collaboration Tool | Task tracking, communication and progress monitoring | Project-wide | All phases | Throughout project | Supports execution tracking
Cloud Platform | Hosting and deployment | Deployment activities | Deployment | As scheduled | Supports production environment
3. Hardware Resources
Resource | Responsibility | Assigned Activities | Project Phase | Allocation | Notes
Development laptops | Programming, analysis and documentation | Project-wide | All phases | Throughout project | Required for team members
Cloud/server infrastructure | Database, AI solution and application hosting | Technical activities | Development / Deployment | As scheduled | Supports scalable execution
Reliable internet connection | Remote collaboration and cloud access | Project-wide | All phases | Throughout project | Required for remote project work
Presentation equipment | Demonstrations and training | A30, A31, A35 | Training / Closure | As required | Supports stakeholder demonstrations
4. External Services
Resource | Responsibility | Assigned Activities | Project Phase | Allocation | Notes
Cloud hosting | Production deployment | A27–A28 | Deployment | As scheduled | External infrastructure service
Cloud storage | Data storage and backup | Data / deployment activities | Data / Deployment | As required | Supports backup and recovery
Internet service | Remote project execution | Project-wide | All phases | Throughout project | External connectivity service
Technical support | Deployment and troubleshooting | A28–A29 | Deployment / Testing | As required | Used when specialist support is needed

## Project Budget
AI-Powered Customer Intelligence Transformation Project
Project Budget
Budget Category | Description | Estimated Cost (₦) | Assumption / Basis
Personnel | Project team costs covering project management, business analysis, data analysis, AI engineering, cloud engineering, software development, QA and change management. | 4500000 | Planning estimate for the multidisciplinary project team.
Software Licences | Paid software and subscriptions required where applicable. | 600000 | Allowance for licences/subscriptions; open-source tools such as PostgreSQL and Python are assumed to have no licence cost.
Hardware | Development laptops and other required technical equipment. | 1500000 | Planning allowance for project hardware and equipment.
Cloud Services | Cloud hosting, storage, computing and deployment infrastructure. | 900000 | Estimated project-period cloud usage.
Training | User training, adoption support and training materials. | 400000 | Estimated cost for implementation and user readiness.
Subtotal |  | 7900000
Contingency Reserve | 10% of subtotal reserved for unforeseen project costs. | 790000 | 10% planning reserve.
TOTAL PROJECT BUDGET |  | 8690000