## Read Me
HealthConnect Week 8 – Final PM Package
Programme | AnalystLab Africa Experience Lab
Week | Week 8
Track | Project Management
Project | HealthConnect Clinic Experience Lab
Project Title | Improving Patient Appointment Attendance and Healthcare Support Using Data and AI
Overall readiness | Conditional – verified PM/Data Analytics evidence is available; other technical outputs remain unverified by PM.
Status rule | Do not mark technical workstreams complete without supporting evidence.

## Final Project Status
Area | Status | Evidence / Basis | PM Action
Project Management coordination | Completed / Finalising | Week 4–7 PM artefacts and Week 8 package. | Consolidate status, risks, dependencies, decisions and presentation.
Data Analytics → PM | Verified | Week 7 no-show-rate validation passed. | Carry verified finding into final project evidence.
Data Science | Pending Evidence | No final DS evidence available to PM. | Do not claim final model readiness.
ML Engineering | Pending Evidence | No final ML evidence available to PM. | Do not claim final pipeline readiness.
Generative AI | Pending Evidence | No final GenAI evidence available to PM. | Do not claim final assistant readiness.
Full end-to-end integration | Conditional | Complete technical evidence unavailable to PM. | Present as conditional readiness.

## Week 7 to Week 8 Transition
Requirement | Response
Main Week 7 output | Testing, validation and project readiness controls.
Most important testing result | Data Analytics No-Show Rate by Previous No-Show Group validation passed.
Major issue / limitation | Final technical workstream evidence was unavailable for PM verification.
Refinement | Testing evidence was incorporated into project status and readiness controls.
Component considered ready | Verified Data Analytics finding used in PM coordination.
Still needs integration | Final technical outputs and complete end-to-end integration evidence.
Tracks involved | Data Analytics → PM is directly evidenced; other pathways remain unverified.
Presentation intent | Problem, evidence, PM coordination, integration logic, business value and limitations.

## Final Workstream Status
Workstream | Status | Evidence Position
Project Management | Ready / Finalising | PM artefacts and final readiness package prepared.
Data Analytics | Verified for supplied testing evidence | Week 7 validation passed.
Data Science | Pending Evidence | No final output available for PM verification.
ML Engineering | Pending Evidence | No final output available for PM verification.
Generative AI | Pending Evidence | No final output available for PM verification.
Full end-to-end technical integration | Conditional | Cannot be independently verified from available PM evidence.

## Data Analytics Validation Evide
Previous No-Show Group | Total Appointments | No-Show Appointments | No-Show Rate | Result
0 | 2921 | 1271 | 43.5% | PASS
1–2 | 1986 | 1088 | 54.8% | PASS
3+ | 93 | 64 | 68.8% | PASS
Total | 5000 | 2423 | 48.5% | PASS

## Final Integration Record
ID | Relationship | Output Received | What PM Did | What Changed | Evidence | Status
FIN-001 | Data Analytics → PM | Week 7 validated no-show-rate result. | Reviewed underlying counts, recorded PASS and incorporated result into readiness records. | No numerical correction; result became verified PM project evidence. | 2,921/1,271 = 43.5%; 1,986/1,088 = 54.8%; 93/64 = 68.8%. | Verified
FIN-002 | Data Science → PM | Not available. | No unsupported integration claimed. | Status remains pending. | No final DS evidence available. | Pending Evidence
FIN-003 | ML Engineering → PM | Not available. | No unsupported integration claimed. | Status remains pending. | No final ML evidence available. | Pending Evidence
FIN-004 | GenAI → PM | Not available. | No unsupported integration claimed. | Status remains pending. | No final GenAI evidence available. | Pending Evidence

## Issues & Dependencies
ID | Type | Description | Impact | Status | PM Treatment
W8-ISS-001 | Evidence | Final Data Science output unavailable to PM. | Cannot confirm model readiness. | Pending Evidence | Do not claim completion.
W8-ISS-002 | Evidence | Final ML Engineering output unavailable to PM. | Cannot confirm pipeline readiness. | Pending Evidence | Do not claim completion.
W8-ISS-003 | Evidence | Final GenAI output unavailable to PM. | Cannot confirm assistant readiness. | Pending Evidence | Do not claim completion.
W8-DEP-001 | Dependency | Full end-to-end integration requires technical evidence from relevant workstreams. | Limits overall readiness confirmation. | Open | Assess overall readiness as conditional.

## Final Risk Register
ID | Risk | Likelihood | Impact | Response | Status
W8-R001 | Incomplete technical evidence | Medium | High | Use evidence-based statuses. | Open
W8-R002 | Full end-to-end integration cannot be verified by PM | Medium | High | State conditional readiness. | Open
W8-R003 | Presentation could overstate readiness | Medium | High | Use verified evidence and explicit limitations. | Controlled
W8-R004 | Analytics findings could be overstated | Low | Medium | Present patterns as observed, not causal. | Controlled

## Final Decision Log
ID | Decision | Reason | Status
DEC-W8-001 | Use evidence-based final statuses. | Missing evidence must not be treated as completion. | Approved
DEC-W8-002 | Carry validated Data Analytics finding into final evidence. | Week 7 validation passed. | Approved
DEC-W8-003 | Do not claim DS/ML/GenAI readiness without evidence. | No final evidence available to PM. | Approved
DEC-W8-004 | Overall readiness is conditional. | Full technical integration cannot be independently verified. | Approved

## Presentation Coordination
Section | Content | Evidence Status
Problem | HealthConnect missed appointments and patient support. | Verified
Data | Appointment dataset and approved project resources. | Verified
Analytics | Validated no-show patterns. | Verified for supplied evidence
Predictive Component | Data Science contribution. | Pending Evidence
ML Engineering | Technical workflow. | Pending Evidence
GenAI | Administrative support component. | Pending Evidence
Project Management | Planning, coordination, risks, dependencies, testing and readiness. | Verified
Final Solution | How components are intended to connect. | Conditional
Business Value | Potential support for attendance and administrative coordination. | Evidence-based
Limitations | Dataset and technical evidence limitations. | Verified

## Readiness Assessment
Area | Assessment | Conclusion
PM documentation | Ready | Ready for submission/presentation.
Verified analytics evidence | Ready for tested component | Validation passed.
Cross-track integration | Partial | Data Analytics → PM verified.
Technical workstreams | Pending Evidence | Cannot confirm DS/ML/GenAI readiness.
End-to-end solution | Conditional | Full readiness cannot be independently verified.
Individual PM presentation | Ready | PM contribution and verified evidence available.

## Outstanding Actions
ID | Action | Priority | Status
ACT-001 | Include verified Data Analytics validation in final presentation. | High | Completed
ACT-002 | State technical evidence limitations clearly. | High | Completed
ACT-003 | Finalise PM closure/status report. | High | In Progress
ACT-004 | Prepare individual 5–10 minute PM presentation. | High | Planned
ACT-005 | Update GitHub README with Week 8 closure. | Medium | Planned