HEALTHCONNECT CLINIC

Week 8 Final Project Management & Readiness Report

Project: HealthConnect Clinic Experience Lab

Project Title: Improving Patient Appointment Attendance and Healthcare Support Using Data and AI

Programme: AnalystLab Africa Experience Lab

Professional Track: Project Management

Reporting Period: Week 8

Version: 1.0

# 1. Executive Status

Week 8 is the final integration, readiness and presentation stage. The Project Management contribution consolidates the planning, execution, integration, testing, risk, dependency, decision and readiness controls developed from Weeks 4–7.

The final PM assessment is evidence-based. Data Analytics → Project Management testing evidence is verified. Final technical evidence from Data Science, ML Engineering and Generative AI was not available to the PM intern for independent verification; these components are therefore not represented as completed.

# 2. Week 7 → Week 8 Transition

| Requirement | Response |
| --- | --- |
| Main Week 7 output | Testing, validation and project readiness controls. |
| Most important testing result | Data Analytics No-Show Rate by Previous No-Show Group validation passed. |
| Major issue / limitation | Final technical evidence unavailable for PM verification. |
| Refinement | Testing evidence incorporated into project status and readiness controls. |
| Component considered ready | Verified Data Analytics finding used in PM coordination. |
| Still needs integration | Final technical outputs and complete end-to-end evidence. |
| Tracks involved | Data Analytics → PM directly evidenced; other pathways unverified. |
| Presentation intent | Problem, evidence, PM coordination, business value and limitations. |

# 3. Final Integration Readiness

Final PM component: HealthConnect Final Project Management & Readiness Package.

The PM component addresses coordination of multidisciplinary work, dependency monitoring, evidence-based status, risk and decision management, readiness assessment and final presentation coordination.

Week 7 improved the PM layer by incorporating verified testing evidence into project-level readiness records.

# 4. Verified Cross-Track Integration

Integration pathway: Data Analytics → Project Management.

The Data Analytics testing output verified the No-Show Rate by Previous No-Show Group against the underlying appointment and no-show counts.

| Group | Appointments | No-Shows | Rate | Result |
| --- | --- | --- | --- | --- |
| 0 previous no-shows | 2,921 | 1,271 | 43.5% | PASS |
| 1–2 previous no-shows | 1,986 | 1,088 | 54.8% | PASS |
| 3+ previous no-shows | 93 | 64 | 68.8% | PASS |
| Total | 5,000 | 2,423 | 48.5% | PASS |

No calculation inconsistency was identified and no corrective numerical change was required. The PM contribution was to convert the verified testing output into documented project evidence for status tracking and final readiness planning.

# 5. Final Workstream Status

| Workstream | Status | Evidence Position |
| --- | --- | --- |
| Project Management | Ready / Finalising | PM artefacts and final readiness package prepared. |
| Data Analytics | Verified for supplied testing evidence | Week 7 validation passed. |
| Data Science | Pending Evidence | No final output available for PM verification. |
| ML Engineering | Pending Evidence | No final output available for PM verification. |
| Generative AI | Pending Evidence | No final output available for PM verification. |
| Full end-to-end technical integration | Conditional | Cannot be independently verified from available PM evidence. |

# 6. Issues, Dependencies and Risks

Final Data Science evidence remains pending.

Final ML Engineering evidence remains pending.

Final Generative AI evidence remains pending.

Full end-to-end integration remains conditional.

Presentation content for unverified technical components must not imply completion.

# 7. Major Project Decisions

Use evidence-based final workstream statuses rather than assuming completion.

Carry the validated Data Analytics finding into the final project evidence.

Do not claim final readiness for technical workstreams without supporting evidence.

Assess overall readiness as conditional where full technical integration cannot be verified.

# 8. Final Presentation Coordination

- Problem — Explain the HealthConnect missed-appointment and patient-support problem.

- Data — Explain the approved appointment dataset and project resources.

- Analytics — Present verified no-show findings and testing evidence.

- Predictive Component — Present only verified Data Science evidence; otherwise identify it as pending.

- ML Engineering — Present only verified pipeline evidence; otherwise identify it as pending.

- GenAI — Present only verified assistant evidence; otherwise identify it as pending.

- Project Management — Explain planning, coordination, dependencies, testing, risks, decisions and readiness.

- Final Solution — Explain intended component connections without overstating unverified execution.

- Business Value — Connect verified evidence to the HealthConnect objective.

- Limitations — Explain evidence availability, dataset limitations and the distinction between observed patterns and causal conclusions.

# 9. Project Readiness Assessment

| Area | Assessment | Conclusion |
| --- | --- | --- |
| PM documentation | Ready | Ready for submission/presentation. |
| Verified analytics evidence | Ready for tested component | Validation passed. |
| Cross-track evidence | Partial | Data Analytics → PM verified. |
| Final technical workstreams | Pending Evidence | PM cannot confirm DS/ML/GenAI readiness. |
| End-to-end solution | Conditional | Full multidisciplinary readiness cannot be independently verified. |
| Individual PM presentation | Ready | PM contribution and verified evidence are available. |

# 10. Project Closure Summary

The Project Management track established and maintained the project control layer across the HealthConnect journey: planning, task execution, timeline management, risks, dependencies, integration, testing, issue tracking, decisions and readiness assessment.

The verified Data Analytics testing result was incorporated into the final PM evidence base. The result remained unchanged after validation: 43.5% for 0 previous no-shows, 54.8% for 1–2, and 68.8% for 3+, with an overall rate of 48.5%.

Overall readiness is conditional because final technical evidence from Data Science, ML Engineering and Generative AI was not available for PM verification. This limitation is documented rather than replaced with assumptions.

# 11. PM Contribution to the HealthConnect Objective

The PM contribution supports the overall objective by creating a structured mechanism for moving evidence from individual workstreams into coordinated project decisions, monitoring dependencies and risks, validating what is ready, and communicating the final solution clearly.