## Slide 1
1
HealthConnect Clinic Experience Lab
Improving Patient Appointment Attendance and Healthcare Support Using Data and AI
Week 8 Final Integration & Project Showcase Project Management Track
HealthConnect Clinic Experience Lab • Project Management Track

## Slide 2
My Project Management Contribution
2
01
Project Charter & Scope
02
Stakeholder Register & WBS
03
Timeline & Task Tracking
04
Risk & Dependency Management
05
Integration & Testing Coordination
06
Decision & Readiness Management
HealthConnect Clinic Experience Lab • Project Management Track

## Slide 3
How the Project Progressed
3
Week 4
Problem Understanding & Planning
Week 5
Analysis & Development
Week 6
Integration & Validation
Week 7
Testing & Refinement
Week 8
Final Integration & Presentation
HealthConnect Clinic Experience Lab • Project Management Track

## Slide 4
Cross-Track Collaboration
4
COMPONENT RECEIVED
No-Show Rate by Previous
No-Show Group
UNDERLYING EVIDENCE
5,000 appointments 2,423 no-shows Underlying counts + calculated rates
TEST RESULT
PASS 43.5% 54.8% 68.8%
HealthConnect Clinic Experience Lab • Project Management Track

## Slide 5
What Changed Because of the Collaboration
5
BEFORE
Analytical finding existed Previous no-show history was associated with different no-show rates.
TESTING
Underlying counts reviewed Rates verified Result: PASS
AFTER
Validated result documented Added to PM testing records Used in readiness assessment
HealthConnect Clinic Experience Lab • Project Management Track

## Slide 6
Testing & Refinement
6
1 TEST
No-Show Rate by Previous
No-Show Group
2 EXPECTED
43.5% / 54.8% / 68.8%
3 ACTUAL
43.5% / 54.8% / 68.8%
4 RESULT
PASS
5 ACTION
No corrective calculation required
6 RETEST
Output remained consistent
HealthConnect Clinic Experience Lab • Project Management Track

## Slide 7
Final Project Readiness
7
PM Documentation
Ready
Data Analytics Evidence
Verified
Data Science
Pending Evidence
ML Engineering
Pending Evidence
GenAI
Pending Evidence
Full End-to-End Integration
Conditional
HealthConnect Clinic Experience Lab • Project Management Track

## Slide 8
Overall HealthConnect Solution
8
Patient Appointment Data
Data Analytics
Predictive / Technical Components
AI Support
Project Management
Business Objective
Business objective: reduce missed appointments and improve the patient support experience.
Technical workstreams are shown as the intended solution structure; only verified evidence is presented as completed.
HealthConnect Clinic Experience Lab • Project Management Track

## Slide 9
Limitations & Remaining Work
9
• Some technical workstream evidence was unavailable to PM.
• Full end-to-end technical integration could not be independently verified.
• The Data Analytics work has documented dataset limitations.
• Further technical testing and integration evidence may be required.
• Final communication should distinguish verified results from pending evidence.
HealthConnect Clinic Experience Lab • Project Management Track

## Slide 10
Closing: Key Lessons
10
1
Plan before execution
2
Track evidence, not assumptions
3
Manage dependencies actively
4
Test before declaring readiness
5
Document decisions and limitations
6
Communicate technical work in business terms
Thank you.
HealthConnect Clinic Experience Lab • Project Management Track