HEALTHCONNECT WEEK 8 PROJECT SUMMARY

Project Management Track

Project: HealthConnect Clinic Experience Lab

Project Title: Improving Patient Appointment Attendance and Healthcare Support Using Data and AI

# 1. Planned for Week 8

Complete final project integration, assess readiness, consolidate status, update risks/dependencies, coordinate presentation structure and prepare closure documentation.

# 2. What was completed

The PM final readiness structure was prepared using verified evidence from the project record. The Data Analytics testing result was incorporated into final status and readiness planning.

# 3. Most important result

The Data Analytics validation passed: 43.5% for 0 previous no-shows, 54.8% for 1–2, 68.8% for 3+, and 48.5% overall.

# 4. Final integration contribution

Data Analytics → PM was used as the verified final cross-track evidence pathway.

# 5. Major limitation

Final technical evidence from Data Science, ML Engineering and Generative AI was not available for PM verification.

# 6. Final project status

PM: Ready/Finalising. Data Analytics: verified for supplied testing evidence. DS, ML Engineering and GenAI: Pending Evidence. Full end-to-end integration: Conditional.

# 7. Key PM decisions

Use evidence-based statuses; carry validated analytics evidence into the final record; do not claim unverified technical completion; assess overall readiness as conditional.

# 8. Presentation focus

Problem, data, verified analytics, PM coordination, intended integration, business value and limitations.

# 9. PM contribution

Planning, execution, integration, testing, risk/dependency management, decision tracking, readiness assessment and presentation coordination.

# 10. Closure

The PM layer and verified analytics evidence are documented. The broader solution must distinguish verified outputs from technical components not independently verified by PM.